## Cover
Requirements Traceability Matrix
Merchant Payment Operations & Dispute Hub
Document | Requirements Traceability Matrix (RTM)
Version | 1.0
Reporting date | 2026-09-10
Prepared by | Bhawna, Product Owner
Test phase | System integration testing (SIT) in progress; UAT, non-functional and security testing planned
Companion documents | Product_Backlog (US- IDs), RAID_Log (R-, A-, I-, D- IDs) and Change_Log (CR- IDs) workbooks
Project type | Simulation / portfolio project prepared to demonstrate Product Owner practice. Not an actual client system; teams, dates, results and controls are illustrative.
Purpose
Shows that every approved requirement is built, tested and evidenced. Each requirement traces forward to user stories and test cases, and each compliance control traces to the requirements and tests that prove it. The Dashboard highlights coverage gaps, failing or blocked tests, open defects and controls without evidence.
Traceability chain
Business requirement (BR) → User story (US, in the Product Backlog) → Test case (TC) → Execution result → Defect (DEF), if the test fails
Compliance control (CTL) → Linked requirements (BR) → Test cases tagged with the control → Evidence for compliance sign-off
Links are recorded by ID. Counts and statuses on the Requirements and Controls tabs calculate from the Test Cases and Defects tabs.
Coverage status (Requirements tab)
Status | Meaning
Verified | All linked test cases have passed.
Partially verified | Some linked tests have passed; the rest haven't run yet. None have failed or are blocked.
Not yet tested | Test cases exist but none have run.
Blocked | At least one linked test can't run because of a dependency or issue, and none have failed.
Failing | At least one linked test has failed. Check the Defects tab.
No test coverage | Approved requirement with no test cases. This is a gap to close before UAT.
Not in scope yet | Requirement is pending a decision, deferred or withdrawn, so coverage isn't expected.
Test phases
Phase | Scope
SIT | System integration testing by the delivery team during sprints, against the processor sandbox.
UAT | User acceptance testing by pilot merchants and dispute ops in the UAT environment.
NFR | Non-functional testing: accessibility and performance.
Security | Independent security validation by InfoSec, including penetration testing and redaction accuracy.
How to maintain this matrix
1. Add a requirement row once it is approved; link stories and any compliance controls by ID.
2. Write at least one test case for every approved requirement before its stories enter a sprint.
3. Update execution status and date after each test run; log a defect for every failure and put its ID on the test case.
4. Review the Dashboard gaps list weekly with QA and Compliance, and before sprint reviews and UAT entry.
5. Detailed test steps and evidence attachments live in the test management tool (for example Jira with Xray or Zephyr); this matrix holds the traceability view.
6. Grey columns calculate automatically. Exact regulatory clause references should be confirmed with the client's compliance team.
Version history
Version | Date | Author | Change summary
1.0 | 2026-09-10 | Bhawna | Initial matrix covering Sprints 1–4 SIT results and planned tests for remaining MVP scope.

## Dashboard
Traceability & Test Coverage Dashboard
Merchant Payment Operations & Dispute Hub · Simulation project · Figures update automatically
Reporting date: 10-Sep-2026
Summary
Approved requirements | Requirements with tests |  | % with tests | Verified | Test cases | % executed | Pass rate
22 | 21 |  | 95.45% | 2 | 62 | 35.48% | 90.91%
Open defects | High / Critical open |  | Failing reqs | Blocked reqs | Reqs with no tests | Controls without tests | Controls failing
2 | 2 |  | 2 | 1 | 1 | 1 | 1
Requirement coverage status
Status |  | Requirements |  | Meaning
Verified |  | 2 |  | All linked tests passed
Partially verified |  | 4 |  | Some passed, rest not yet run
Not yet tested |  | 12 |  | Tests written, none run
Blocked |  | 1 |  | A linked test can't run
Failing |  | 2 |  | A linked test failed
No test coverage |  | 1 |  | Approved but no tests: gap
Not in scope yet |  | 2 |  | Pending decision or deferred
Coverage by requirement category (approved requirements)
Category |  | Approved | With tests | Verified | Needs attention | Coverage %
Functional |  | 8 | 8 | 2 | 0 | 100%
Integration |  | 2 | 2 | 0 | 1 | 100%
Security |  | 3 | 3 | 0 | 1 | 100%
Compliance |  | 4 | 3 | 0 | 1 | 75%
Non-functional |  | 2 | 2 | 0 | 0 | 100%
Reporting |  | 1 | 1 | 0 | 0 | 100%
Data Quality |  | 1 | 1 | 0 | 0 | 100%
Analytics |  | 1 | 1 | 0 | 1 | 100%
Test execution by phase
Phase |  | Total | Passed | Failed | Blocked | Not Run | % executed
SIT |  | 54 | 20 | 2 | 2 | 30 | 40.74%
UAT |  | 3 | 0 | 0 | 0 | 3 | 0%
NFR |  | 3 | 0 | 0 | 0 | 3 | 0%
Security |  | 2 | 0 | 0 | 0 | 2 | 0%
Total |  | 62 | 20 | 2 | 2 | 38 | 35.48%
Requirements needing attention (failing, blocked or no test coverage)
Req ID | Requirement | Coverage status | Failed | Blocked | Open defects | Linked stories | Linked RAID / CR
BR-02 | Merchant users sign in with company single sign-on and receive role-based access (Admin, Finance, Operations). | Failing | 1 | 0 | 1 | US-001, US-002, US-003 | A-03, D-02
BR-06 | New disputes are received from the processor automatically without duplicates, and status changes are reflected within 5 minutes. | Failing | 1 | 1 | 1 | US-018, US-019, US-020 | A-02, I-01, D-01
BR-20 | Product team can measure pilot adoption without collecting personal or card data. | Blocked | 0 | 1 | 0 | US-034, US-005 | R-04, I-06
BR-22 | Evidence files are retained and deleted in line with the records retention policy. | No test coverage | 0 | 0 | 0 | US-014 | A-07
Compliance control assurance
Control ID | Framework / Policy | Tests | Passed | Failed | Assurance status | Owner | Sign-off
CTL-01 | PCI DSS | 5 | 0 | 0 | Not yet tested | Compliance Lead | Not Started
CTL-02 | PCI DSS / Security Policy | 2 | 0 | 0 | Not yet tested | InfoSec Lead | Not Started
CTL-03 | Internal Audit Policy | 2 | 0 | 0 | Not yet tested | Compliance Lead | Not Started
CTL-04 | Data Privacy | 3 | 0 | 0 | Not yet tested | Data Protection Lead | Not Started
CTL-05 | Access Control Policy | 6 | 2 | 1 | Failing | InfoSec Lead | Not Started
CTL-06 | Card Network Rules | 5 | 4 | 0 | Partially evidenced | Dispute Ops Lead | Not Started
CTL-07 | Accessibility (WCAG 2.1 AA) | 2 | 0 | 0 | Not yet tested | UX Designer | Not Started
CTL-08 | Security Testing Policy | 1 | 0 | 0 | Not yet tested | InfoSec Lead | Not Started
CTL-09 | Records Retention Policy | 0 | 0 | 0 | No test coverage | Legal Counsel | Not Started

## Requirements
Requirements
Merchant Payment Operations & Dispute Hub · Simulation project · One row per approved or proposed requirement
Grey columns calculate automatically. Edit white columns only; use dropdowns where provided.
Req ID | Category | Requirement | Source / Rationale | Priority | Business Owner | Epic | Linked User Stories | Linked Controls | Linked RAID / CR | Verification Method | Requirement Status | Tests Linked | Passed | Failed | Blocked | Not Run | Open Defects | Coverage Status | UAT Sign-off | Notes | Gap helper
BR-01 | Functional | Merchants can view all open disputes, their status and response deadlines in one self-service portal. | Discovery interviews with pilot merchants | Must | Dispute Ops Lead | EP-02 | US-006, US-008, US-009, US-011 |  | R-03 | Test | Approved | 6 | 4 | 0 | 0 | 2 | 0 | Partially verified | Not Started
BR-02 | Security | Merchant users sign in with company single sign-on and receive role-based access (Admin, Finance, Operations). | Security architecture review; IAM workshop | Must | Product Owner | EP-01 | US-001, US-002, US-003 | CTL-05 | A-03, D-02 | Test | Approved | 5 | 2 | 1 | 0 | 2 | 1 | Failing | Not Started |  | 6
BR-03 | Functional | Merchants can upload evidence and submit a dispute response to the processor before the deadline. | Discovery interviews; dispute ops process walkthrough | Must | Dispute Ops Lead | EP-03 | US-012, US-015, US-017 | CTL-09 | D-01, I-03 | Test | Approved | 5 | 0 | 0 | 0 | 5 | 0 | Not yet tested | Not Started
BR-04 | Compliance | Full card numbers are never stored or displayed in evidence, exports or analytics. | PCI DSS scope assessment; CR-03 | Must | Compliance Lead | EP-03 | US-013, US-014, US-030, US-034 | CTL-01, CTL-02 | R-02, CR-03 | Test | Approved | 5 | 0 | 0 | 0 | 5 | 0 | Not yet tested | Not Started | InfoSec validation of redaction accuracy is a condition of CR-03.
BR-05 | Functional | Merchants can accept a dispute without contesting it. | Dispute ops process walkthrough | Should | Dispute Ops Lead | EP-03 | US-016 |  |  | Test | Approved | 2 | 2 | 0 | 0 | 0 | 0 | Verified | Not Started
BR-06 | Integration | New disputes are received from the processor automatically without duplicates, and status changes are reflected within 5 minutes. | Solution design; processor API review | Must | Tech Lead | EP-04 | US-018, US-019, US-020 |  | A-02, I-01, D-01 | Test | Approved | 7 | 4 | 1 | 1 | 1 | 1 | Failing | Not Started |  | 10
BR-07 | Compliance | Dispute reason codes and response windows can be updated without a code release, with a history of each change. | Card network rule change risk (R-01); CR-02 | Must | Dispute Ops Lead | EP-04 | US-021, US-022 | CTL-06 | R-01, CR-02, I-02 | Test | Approved | 3 | 2 | 0 | 0 | 1 | 0 | Partially verified | Not Started
BR-08 | Functional | Ops are alerted when the processor feed stops updating, and merchants can see when data was last synced. | Deadline risk review (R-03); CR-07 | Must | Dispute Ops Lead | EP-04 | US-010, US-023 |  | R-03, CR-07 | Test | Approved | 3 | 2 | 0 | 0 | 1 | 0 | Partially verified | Not Started
BR-09 | Functional | Merchants receive reminders before deadlines and notifications of dispute outcomes, and can opt out of emails. | Merchant feedback; privacy review | Must | Product Owner | EP-05 | US-025, US-026 | CTL-04 | R-03 | Test | Approved | 3 | 0 | 0 | 0 | 3 | 0 | Not yet tested | Not Started | SMS reminders (CR-09) not included until assessed.
BR-10 | Functional | Merchants can view settlements, including chargeback debits and reversals, and export them to CSV. | Finance user interviews; CR-08 | Must | Finance Lead | EP-06 | US-028, US-029, US-030 | CTL-01 | D-04, CR-08 | Test | Approved | 3 | 0 | 0 | 0 | 3 | 0 | Not yet tested | Not Started
BR-11 | Reporting | Ops and finance report dispute outcomes and win rate using one agreed definition. | Reporting workshop; I-05 | Must | Finance Lead | EP-07 | US-031, US-032 |  | I-05, CR-05 | Test | Approved | 2 | 0 | 0 | 0 | 2 | 0 | Not yet tested | Not Started | Expected results for outcome tests will be finalized after the CR-05 decision.
BR-12 | Data Quality | Settlement data reconciles to the finance ledger within 0.5% before merchant reports are released. | Data quality risk (R-05) | Must | Finance Lead | EP-07 | US-033 |  | R-05, D-04 | Analysis | Approved | 2 | 0 | 0 | 0 | 2 | 0 | Not yet tested | Not Started
BR-13 | Compliance | All evidence actions are recorded in an audit history that users can't edit. | Internal audit policy | Must | Compliance Lead | EP-01 | US-004 | CTL-03 | A-07 | Test | Approved | 2 | 0 | 0 | 0 | 2 | 0 | Not yet tested | Not Started
BR-14 | Security | Evidence files are encrypted at rest and in transit. | Security architecture review | Must | Tech Lead | EP-09 | US-041 | CTL-02 | R-02, R-08 | Inspection | Approved | 2 | 0 | 0 | 0 | 2 | 0 | Not yet tested | Not Started
BR-15 | Non-functional | Merchant portal screens meet WCAG 2.1 AA. | Accessibility policy; R-10 | Must | UX Designer | EP-09 | US-042 | CTL-07 | R-10 | Test | Approved | 2 | 0 | 0 | 0 | 2 | 0 | Not yet tested | Not Started
BR-16 | Non-functional | 95th percentile API response stays under 2 seconds at 3x forecast peak volume. | Capacity planning; R-09 | Must | Tech Lead | EP-09 | US-043 |  | R-09 | Test | Approved | 1 | 0 | 0 | 0 | 1 | 0 | Not yet tested | Not Started
BR-17 | Security | Critical and high penetration test findings are fixed and retested before go-live. | Security go-live policy | Must | Compliance Lead | EP-09 | US-044 | CTL-08 | D-03, CR-06 | Test | Approved | 1 | 0 | 0 | 0 | 1 | 0 | Not yet tested | Not Started
BR-18 | Functional | Dispute ops work disputes from a prioritized queue, including disputes with unmapped reason codes. | Dispute ops process walkthrough; I-02 | Must | Dispute Ops Lead | EP-08 | US-035, US-022 |  | I-02 | Test | Approved | 3 | 2 | 0 | 0 | 1 | 0 | Partially verified | Not Started
BR-19 | Integration | Servicing agents can retrieve a merchant's dispute status through an API for their agent console. | Customer servicing request; D-06 | Should | Product Owner | EP-04 | US-024 | CTL-05 | D-06 | Test | Approved | 2 | 0 | 0 | 0 | 2 | 0 | Not yet tested | Not Started
BR-20 | Analytics | Product team can measure pilot adoption without collecting personal or card data. | Pilot success criteria; I-06 | Must | Product Owner | EP-07 | US-034, US-005 | CTL-04 | R-04, I-06 | Test | Approved | 1 | 0 | 0 | 1 | 0 | 0 | Blocked | Not Started |  | 24
BR-21 | Functional | Dispute reasons are shown in plain language with suggested evidence types. | Merchant feedback in discovery | Should | Dispute Ops Lead | EP-02 | US-007 | CTL-06 | I-02 | Test | Approved | 2 | 2 | 0 | 0 | 0 | 0 | Verified | Not Started
BR-22 | Compliance | Evidence files are retained and deleted in line with the records retention policy. | Records retention policy; A-07 | Must | Compliance Lead | EP-03 | US-014 | CTL-09 | A-07 | Test | Approved | 0 | 0 | 0 | 0 | 0 | 0 | No test coverage | Not Started | Test cases to be written once A-07 confirms retention rules. | 26
BR-23 | Functional | Dispute ops can see a linked fraud case reference on a dispute. | Fraud operations request; CR-01 | Should | Dispute Ops Lead | EP-08 | US-036 |  | CR-01, D-07 | Test | Pending decision | 0 | 0 | 0 | 0 | 0 | 0 | Not in scope yet | Not Started | In scope only if CR-01 Option C is approved.
BR-24 | Functional | Merchant portal is available in Spanish. | Relationship team request; CR-04 | Won't (this release) | Product Owner | EP-01 | US-046 |  | CR-04, A-04 | Test | Deferred | 0 | 0 | 0 | 0 | 0 | 0 | Not in scope yet | Not Started | Deferred to Phase 2 via CR-04.

## Test Cases
Test Cases
Merchant Payment Operations & Dispute Hub · Simulation project · Detailed steps are held in the test management tool
Grey columns calculate automatically. Edit white columns only; use dropdowns where provided.
Test Case ID | Req ID | Requirement | Story ID | Control ID | Test Type | Test Phase | Test Scenario | Preconditions | Expected Result | Tester | Execution Status | Execution Date | Environment | Defect IDs | Notes
TC-001 | BR-01 | Merchants can view all open disputes, their status and response deadlines in one self-service portal. | US-006 |  | Functional | SIT | Inbox lists open disputes with key fields | Merchant has at least 5 open disputes | Each dispute shows ID, amount, reason, status and due date. | QA Analyst | Passed | 2026-08-13 | SIT
TC-002 | BR-01 | Merchants can view all open disputes, their status and response deadlines in one self-service portal. | US-006 |  | Functional | SIT | Paging keeps sort order beyond 50 disputes | Merchant has 120 open disputes sorted by due date | Page 2 and later continue in due-date order with no repeats or gaps. | QA Analyst | Passed | 2026-08-20 | SIT | DEF-01 | Failed on 14-Aug; passed on retest after DEF-01 fix.
TC-003 | BR-01 | Merchants can view all open disputes, their status and response deadlines in one self-service portal. | US-008 |  | Functional | SIT | Filter by status, reason and due date range | Disputes exist across statuses and due dates | Only disputes matching all filters are shown, including those due on the range end date. | QA Analyst | Passed | 2026-08-27 | SIT | DEF-04 | Passed on retest after DEF-04 fix.
TC-004 | BR-01 | Merchants can view all open disputes, their status and response deadlines in one self-service portal. | US-009 |  | Functional | SIT | Dispute detail shows dated timeline | Dispute has at least 3 status changes | Timeline lists each status change with date in time order. | QA Analyst | Passed | 2026-08-27 | SIT
TC-005 | BR-01 | Merchants can view all open disputes, their status and response deadlines in one self-service portal. | US-011 |  | Functional | SIT | Disputes due within 2 days shown in red at top | Disputes due in 1, 4 and 10 days | 1-day dispute red at top; 4-day dispute amber; 10-day dispute unhighlighted. | QA Analyst | Not Run |  | SIT |  | Story in progress in Sprint 4.
TC-006 | BR-01 | Merchants can view all open disputes, their status and response deadlines in one self-service portal. | US-006 |  | UAT | UAT | Merchant ops user finds and reviews disputes due this week | Pilot merchant UAT account with masked data | User identifies all disputes due within 7 days and opens each detail page without help. | Merchant Ops (UAT) | Not Run |  | UAT |  | UAT scripts to be finalized in Sprint 8.
TC-007 | BR-02 | Merchant users sign in with company single sign-on and receive role-based access (Admin, Finance, Operations). | US-001 | CTL-05 | Security | SIT | SSO sign-in lands on inbox | Active merchant user in test identity provider | User signs in through SSO and lands on the dispute inbox. | QA Analyst | Passed | 2026-07-30 | SIT
TC-008 | BR-02 | Merchant users sign in with company single sign-on and receive role-based access (Admin, Finance, Operations). | US-001 | CTL-05 | Security | SIT | Disabled account is denied and logged | Merchant user disabled in identity provider | Access denied; attempt recorded in security log with user and time. | QA Analyst | Passed | 2026-07-30 | SIT
TC-009 | BR-02 | Merchant users sign in with company single sign-on and receive role-based access (Admin, Finance, Operations). | US-001 | CTL-05 | Regression | SIT | Session expires after 15 minutes of inactivity | Signed-in user idle on dispute detail page | After 15 minutes idle, next action requires sign-in. | QA Analyst | Failed | 2026-09-08 | SIT | DEF-02 | Found in Sprint 4 regression run.
TC-010 | BR-02 | Merchant users sign in with company single sign-on and receive role-based access (Admin, Finance, Operations). | US-002 | CTL-05 | Functional | SIT | Admin assigns role and permissions update | Merchant admin and a newly invited user | Invited user receives chosen role; permission change applies on next page load. | QA Analyst | Not Run |  | SIT |  | Depends on D-02 role configuration.
TC-011 | BR-02 | Merchant users sign in with company single sign-on and receive role-based access (Admin, Finance, Operations). | US-003 | CTL-05 | Security | SIT | Finance role can't submit evidence | User with Finance role only | Submit evidence action is hidden and the endpoint rejects direct calls. | QA Analyst | Not Run |  | SIT
TC-012 | BR-03 | Merchants can upload evidence and submit a dispute response to the processor before the deadline. | US-012 |  | Functional | SIT | Upload PDF, JPG and PNG files up to 10 MB | Dispute awaiting evidence | Files attach and list with name, size and upload time. | QA Analyst | Not Run |  | SIT
TC-013 | BR-03 | Merchants can upload evidence and submit a dispute response to the processor before the deadline. | US-012 |  | Functional | SIT | Unsupported or oversize file rejected | Dispute awaiting evidence; 12 MB file and .exe file | Clear error shown for each file; nothing stored. | QA Analyst | Not Run |  | SIT
TC-014 | BR-03 | Merchants can upload evidence and submit a dispute response to the processor before the deadline. | US-015 |  | Integration | SIT | Submit evidence package to processor | Dispute with evidence and response note; processor sandbox | Package accepted by processor; status changes to 'Evidence submitted'; attachments read-only. | QA Analyst | Not Run |  | SIT
TC-015 | BR-03 | Merchants can upload evidence and submit a dispute response to the processor before the deadline. | US-015 |  | Integration | SIT | Processor rejection shown and resubmission allowed | Processor sandbox configured to reject submission | Rejection reason shown; user corrects and resubmits successfully. | QA Analyst | Not Run |  | SIT
TC-016 | BR-03 | Merchants can upload evidence and submit a dispute response to the processor before the deadline. | US-015 |  | UAT | UAT | Merchant uploads and submits evidence end to end | Pilot merchant UAT account; dispute due in 3 days | User submits evidence without help and sees confirmation before deadline. | Merchant Ops (UAT) | Not Run |  | UAT
TC-017 | BR-04 | Full card numbers are never stored or displayed in evidence, exports or analytics. | US-013 | CTL-01 | Security | SIT | Card numbers masked except last four digits | Test files containing full card numbers in text and images | Stored files show only last four digits of each card number. | QA Analyst | Not Run |  | SIT
TC-018 | BR-04 | Full card numbers are never stored or displayed in evidence, exports or analytics. | US-013 | CTL-01 | Security | SIT | Only redacted version is accessible | Redacted file stored for a dispute | Users and APIs can retrieve only the redacted version; original isn't retained. | QA Analyst | Not Run |  | SIT
TC-019 | BR-04 | Full card numbers are never stored or displayed in evidence, exports or analytics. | US-014 | CTL-01 | Security | SIT | Unprocessable file quarantined and merchant notified | Corrupted image file | File quarantined, not attached; merchant receives in-portal message and email. | QA Analyst | Not Run |  | SIT
TC-020 | BR-04 | Full card numbers are never stored or displayed in evidence, exports or analytics. | US-030 | CTL-01 | Security | SIT | CSV exports contain no full card numbers | Disputes and settlements with card data in source | Exported file contains no full card numbers in any column. | QA Analyst | Not Run |  | SIT
TC-021 | BR-04 | Full card numbers are never stored or displayed in evidence, exports or analytics. | US-013 | CTL-01 | Security | Security | InfoSec validates redaction accuracy | Agreed InfoSec test set | Detection accuracy meets the agreed threshold; InfoSec sign-off recorded. | InfoSec | Not Run |  | SIT |  | Condition of CR-03; required before UAT sign-off.
TC-022 | BR-05 | Merchants can accept a dispute without contesting it. | US-016 |  | Integration | SIT | Accept dispute without contesting | Open dispute; processor sandbox | Acceptance sent to processor; status changes to 'Accepted'. | QA Analyst | Passed | 2026-08-27 | SIT
TC-023 | BR-05 | Merchants can accept a dispute without contesting it. | US-016 |  | Functional | SIT | Acceptance confirmation warns amount won't be recovered | Open dispute | Confirmation message states the dispute amount won't be recovered. | QA Analyst | Passed | 2026-08-27 | SIT
TC-024 | BR-06 | New disputes are received from the processor automatically without duplicates, and status changes are reflected within 5 minutes. | US-018 |  | Integration | SIT | New disputes ingested with mandatory fields | Processor sandbox with 20 new disputes | 20 disputes created with all mandatory fields populated. | QA Analyst | Passed | 2026-07-31 | SIT
TC-025 | BR-06 | New disputes are received from the processor automatically without duplicates, and status changes are reflected within 5 minutes. | US-018 |  | Integration | SIT | Re-received dispute creates no duplicate | Dispute already ingested | Second receipt updates nothing new and creates no duplicate. | QA Analyst | Passed | 2026-07-31 | SIT
TC-026 | BR-06 | New disputes are received from the processor automatically without duplicates, and status changes are reflected within 5 minutes. | US-018 |  | Integration | SIT | Invalid record routed to error queue | Sandbox record missing merchant ID | Record placed in error queue with validation reason logged. | QA Analyst | Passed | 2026-07-31 | SIT
TC-027 | BR-06 | New disputes are received from the processor automatically without duplicates, and status changes are reflected within 5 minutes. | US-019 |  | Integration | SIT | Status webhook updates dispute within 5 minutes | Processor sandbox webhook configured | Dispute status and due date update within 5 minutes of the webhook. | QA Analyst | Blocked | 2026-09-03 | SIT |  | Blocked by inconsistent sandbox status values (I-01).
TC-028 | BR-06 | New disputes are received from the processor automatically without duplicates, and status changes are reflected within 5 minutes. | US-019 |  | Security | SIT | Webhook with invalid signature rejected | Webhook with tampered signature | Webhook rejected and logged; dispute unchanged. | QA Analyst | Not Run |  | SIT
TC-029 | BR-06 | New disputes are received from the processor automatically without duplicates, and status changes are reflected within 5 minutes. | US-020 |  | Integration | SIT | Status variants map to one internal status | Sandbox sends UNDER_REVIEW and IN_REVIEW for the same stage | Both variants map to internal status 'Under review'. | QA Analyst | Failed | 2026-09-09 | SIT | DEF-03
TC-030 | BR-06 | New disputes are received from the processor automatically without duplicates, and status changes are reflected within 5 minutes. | US-020 |  | Integration | SIT | Unknown status keeps last status and alerts | Sandbox sends an unrecognized status value | Dispute keeps its previous status; alert raised to ops channel. | QA Analyst | Passed | 2026-09-09 | SIT
TC-031 | BR-07 | Dispute reason codes and response windows can be updated without a code release, with a history of each change. | US-021 | CTL-06 | Functional | SIT | Updated response window applies without code change | Reference data update for one reason code | New disputes with that code use the updated window; no deployment needed. | QA Analyst | Passed | 2026-09-07 | SIT
TC-032 | BR-07 | Dispute reason codes and response windows can be updated without a code release, with a history of each change. | US-021 | CTL-06 | Functional | SIT | Reference data change history kept | Reason code window changed twice | Previous values, change dates and approvers are retrievable. | QA Analyst | Passed | 2026-09-08 | SIT
TC-033 | BR-07 | Dispute reason codes and response windows can be updated without a code release, with a history of each change. | US-022 | CTL-06 | Functional | SIT | Unmapped reason code routes to manual review | Dispute with reason code missing from mapping | Dispute appears in manual review queue with unmapped-code flag. | QA Analyst | Not Run |  | SIT
TC-034 | BR-08 | Ops are alerted when the processor feed stops updating, and merchants can see when data was last synced. | US-010 |  | Functional | SIT | Last synced timestamp shown in user time zone | Users in two different time zones | Timestamp shows correct local date and time for each user. | QA Analyst | Passed | 2026-09-04 | SIT
TC-035 | BR-08 | Ops are alerted when the processor feed stops updating, and merchants can see when data was last synced. | US-010 |  | Functional | SIT | Timestamp warning after 2 hours without sync | Last sync set to 3 hours ago | Timestamp highlighted with warning styling. | QA Analyst | Passed | 2026-09-04 | SIT
TC-036 | BR-08 | Ops are alerted when the processor feed stops updating, and merchants can see when data was last synced. | US-023 |  | Integration | SIT | Ops alert after 2 hours without feed updates | Feed paused during business hours | Alert sent to ops channel after 2 hours; recovery message when feed resumes. | QA Analyst | Not Run |  | SIT
TC-037 | BR-09 | Merchants receive reminders before deadlines and notifications of dispute outcomes, and can opt out of emails. | US-025 | CTL-04 | Functional | SIT | Reminders sent 5 and 2 days before due date | Dispute with no evidence; Operations-role users | Reminder emails sent at 5 and 2 days before due date only. | QA Analyst | Not Run |  | SIT
TC-038 | BR-09 | Merchants receive reminders before deadlines and notifications of dispute outcomes, and can opt out of emails. | US-025 | CTL-04 | Functional | SIT | Opted-out user skipped and opt-out recorded | One Operations user opted out | Opted-out user receives no reminder; opt-out date recorded. | QA Analyst | Not Run |  | SIT
TC-039 | BR-09 | Merchants receive reminders before deadlines and notifications of dispute outcomes, and can opt out of emails. | US-026 |  | Functional | SIT | Outcome notification to Finance and Admin users | Dispute reaches final outcome | Finance and Admin users get in-portal notification and email. | QA Analyst | Not Run |  | SIT
TC-040 | BR-10 | Merchants can view settlements, including chargeback debits and reversals, and export them to CSV. | US-028 |  | Functional | SIT | Settlement summary by payout date | Settlement data loaded for 30 days | Payout date, gross sales, fees, chargeback debits and net payout match source data. | QA Analyst | Not Run |  | SIT
TC-041 | BR-10 | Merchants can view settlements, including chargeback debits and reversals, and export them to CSV. | US-029 |  | Functional | SIT | Chargeback debit and later reversal linked | Dispute debited then won | Debit shown on original payout; reversal on later payout, both linked to the dispute. | QA Analyst | Not Run |  | SIT
TC-042 | BR-10 | Merchants can view settlements, including chargeback debits and reversals, and export them to CSV. | US-030 |  | Functional | SIT | CSV export matches filtered view | Filters applied on settlement list | CSV contains exactly the filtered rows and visible columns. | QA Analyst | Not Run |  | SIT
TC-043 | BR-11 | Ops and finance report dispute outcomes and win rate using one agreed definition. | US-032 |  | Functional | SIT | Each closed dispute counted in one outcome category | Closed disputes including partial reversals | Every closed dispute appears in exactly one outcome category; totals match closed count. | QA Analyst | Not Run |  | SIT |  | Expected result to be confirmed after CR-05 decision.
TC-044 | BR-11 | Ops and finance report dispute outcomes and win rate using one agreed definition. | US-031 |  | UAT | UAT | Ops lead validates dashboard against source data | Dashboard refreshed with UAT data | Volumes and ageing bands match source extract for sample week. | Dispute Ops (UAT) | Not Run |  | UAT
TC-045 | BR-12 | Settlement data reconciles to the finance ledger within 0.5% before merchant reports are released. | US-033 |  | Data | SIT | Sample month reconciles to finance ledger | Sample month loaded; ledger extract from finance | Variance between report and ledger is within 0.5%. | Data Analyst | Not Run |  | SIT
TC-046 | BR-12 | Settlement data reconciles to the finance ledger within 0.5% before merchant reports are released. | US-033 |  | Data | SIT | Records failing quality rules listed with rule | Seeded duplicates and missing merchant IDs | Each seeded record appears in exception report with the failed rule. | Data Analyst | Not Run |  | SIT
TC-047 | BR-13 | All evidence actions are recorded in an audit history that users can't edit. | US-004 | CTL-03 | Security | SIT | Evidence actions recorded in audit history | User uploads, deletes and submits evidence | Each action logged with user, time, dispute ID and action. | QA Analyst | Not Run |  | SIT
TC-048 | BR-13 | All evidence actions are recorded in an audit history that users can't edit. | US-004 | CTL-03 | Security | SIT | Audit records can't be edited | Existing audit records; admin user | No user or API can modify or delete audit records. | QA Analyst | Not Run |  | SIT
TC-049 | BR-14 | Evidence files are encrypted at rest and in transit. | US-041 | CTL-02 | Security | SIT | Stored evidence encrypted with approved key service | Evidence file uploaded | Storage configuration review confirms encryption at rest with approved keys. | InfoSec | Not Run |  | SIT
TC-050 | BR-14 | Evidence files are encrypted at rest and in transit. | US-041 | CTL-02 | Security | SIT | File transfers use TLS 1.2 or higher | Transfer to processor sandbox | Connection scan shows TLS 1.2 or higher; weaker protocols refused. | InfoSec | Not Run |  | SIT
TC-051 | BR-15 | Merchant portal screens meet WCAG 2.1 AA. | US-042 | CTL-07 | Accessibility | NFR | WCAG 2.1 AA audit of MVP screens | All MVP screens in UAT build | No critical or serious WCAG 2.1 AA issues remain. | Accessibility Specialist | Not Run |  | UAT
TC-052 | BR-15 | Merchant portal screens meet WCAG 2.1 AA. | US-042 | CTL-07 | Accessibility | NFR | Keyboard-only upload and submit flow | Keyboard only, screen reader on | Every step in upload and submit can be reached and completed. | Accessibility Specialist | Not Run |  | UAT
TC-053 | BR-16 | 95th percentile API response stays under 2 seconds at 3x forecast peak volume. | US-043 |  | Performance | NFR | Load test at 3x forecast peak for 60 minutes | Performance environment sized like production | 95th percentile API response under 2 seconds throughout. | Performance Engineer | Not Run |  | Perf
TC-054 | BR-17 | Critical and high penetration test findings are fixed and retested before go-live. | US-044 | CTL-08 | Security | Security | Retest critical and high pen test findings | Pen test report issued; fixes deployed | All critical and high findings retested and closed by InfoSec. | InfoSec | Not Run |  | UAT |  | Depends on pen test date (D-03).
TC-055 | BR-18 | Dispute ops work disputes from a prioritized queue, including disputes with unmapped reason codes. | US-035 |  | Functional | SIT | Ops queue lists disputes needing action by due date | Disputes with failed submissions and manual review flags | Queue shows only disputes needing action, ordered by due date with reason. | QA Analyst | Passed | 2026-08-13 | SIT
TC-056 | BR-18 | Dispute ops work disputes from a prioritized queue, including disputes with unmapped reason codes. | US-035 |  | Functional | SIT | Assigned dispute visible to other analysts | Two analyst accounts | Dispute assigned by one analyst shows as assigned for the other. | QA Analyst | Passed | 2026-08-13 | SIT
TC-062 | BR-18 | Dispute ops work disputes from a prioritized queue, including disputes with unmapped reason codes. | US-022 |  | Functional | SIT | Analyst resolves a dispute from the manual review queue | Dispute flagged for unmapped reason code | Analyst assigns a category; dispute leaves the manual review queue and routes normally. | QA Analyst | Not Run |  | SIT
TC-057 | BR-19 | Servicing agents can retrieve a merchant's dispute status through an API for their agent console. | US-024 |  | Integration | SIT | Agent retrieves dispute status within 2 seconds | Authorized servicing test client | Status, due date and last update returned within 2 seconds. | QA Analyst | Not Run |  | SIT
TC-058 | BR-19 | Servicing agents can retrieve a merchant's dispute status through an API for their agent console. | US-024 | CTL-05 | Security | SIT | Unauthorized API caller denied and logged | Client without servicing scope | Request denied and logged. | QA Analyst | Not Run |  | SIT
TC-059 | BR-20 | Product team can measure pilot adoption without collecting personal or card data. | US-034 | CTL-04 | Functional | SIT | Tracked events contain no personal or card data | Approved tracking plan | Captured events contain only approved properties; no personal or card data. | QA Analyst | Blocked |  | SIT |  | Blocked until tracking plan is approved (I-06).
TC-060 | BR-21 | Dispute reasons are shown in plain language with suggested evidence types. | US-007 | CTL-06 | Functional | SIT | Plain-language reason and evidence types shown | Disputes with mapped reason codes | Plain-language description and suggested evidence types shown. | QA Analyst | Passed | 2026-08-13 | SIT
TC-061 | BR-21 | Dispute reasons are shown in plain language with suggested evidence types. | US-007 | CTL-06 | Functional | SIT | Unmapped code shows 'description pending' | Dispute with code lacking description | Raw code shown with 'description pending' label. | QA Analyst | Passed | 2026-08-13 | SIT

## Controls
Compliance Controls
Merchant Payment Operations & Dispute Hub · Simulation project · Frameworks are summarized; confirm exact clause references with the client's compliance team
Grey columns calculate automatically. Edit white columns only; use dropdowns where provided.
Control ID | Framework / Policy | Control Objective | Linked Requirements | Evidence Required | Evidence Location | Control Owner | Tests Linked | Passed | Failed | Assurance Status | Compliance Sign-off | Notes
CTL-01 | PCI DSS | Stored and displayed card numbers are unreadable except for the last four digits. | BR-04, BR-10 | Redaction test results; InfoSec validation report; export sample review | Test management tool; Compliance SharePoint | Compliance Lead | 5 | 0 | 0 | Not yet tested | Not Started | Map to exact PCI DSS requirement numbers with the client's compliance team or QSA.
CTL-02 | PCI DSS / Security Policy | Cardholder and merchant data is encrypted at rest and in transit. | BR-04, BR-14 | Encryption configuration review; TLS scan results | Security evidence repository | InfoSec Lead | 2 | 0 | 0 | Not yet tested | Not Started
CTL-03 | Internal Audit Policy | User actions on evidence are logged and protected from alteration. | BR-13 | Audit log test results; log retention configuration | Test management tool | Compliance Lead | 2 | 0 | 0 | Not yet tested | Not Started
CTL-04 | Data Privacy | Personal data is minimized in analytics and communications, and email opt-outs are honored and recorded. | BR-09, BR-20 | Tracking plan privacy review; opt-out test results | Data governance register | Data Protection Lead | 3 | 0 | 0 | Not yet tested | Not Started | Linked to I-06 tracking plan approval.
CTL-05 | Access Control Policy | Access follows least privilege by role; denied access attempts are logged. | BR-02, BR-19 | Role permission matrix; access test results; IAM configuration export | Test management tool; IAM change records | InfoSec Lead | 6 | 2 | 1 | Failing | Not Started
CTL-06 | Card Network Rules | Dispute reason codes and response windows are kept current, with an approved change history. | BR-07, BR-21 | Reference data change log; network bulletin review record | Dispute ops SharePoint | Dispute Ops Lead | 5 | 4 | 0 | Partially evidenced | Not Started
CTL-07 | Accessibility (WCAG 2.1 AA) | Customer-facing screens conform to WCAG 2.1 AA. | BR-15 | Accessibility audit report; remediation log | UX team repository | UX Designer | 2 | 0 | 0 | Not yet tested | Not Started
CTL-08 | Security Testing Policy | An independent penetration test is completed and critical/high findings are remediated before go-live. | BR-17 | Pen test report; retest confirmation; risk acceptances for open medium/low findings | Security evidence repository | InfoSec Lead | 1 | 0 | 0 | Not yet tested | Not Started | Timing depends on D-03 and CR-06.
CTL-09 | Records Retention Policy | Evidence files are retained and deleted according to the approved retention schedule. | BR-03, BR-22 | Retention configuration; deletion job test results; legal confirmation | Legal & Compliance SharePoint | Legal Counsel | 0 | 0 | 0 | No test coverage | Not Started | Retention rules pending A-07; no test cases yet.

## Defects
Defect Log
Merchant Payment Operations & Dispute Hub · Simulation project · Defects found during test execution
Grey columns calculate automatically. Edit white columns only; use dropdowns where provided.
Defect ID | Test Case ID | Req ID | Story ID | Title | Description | Severity | Status | Raised Date | Raised By | Owner Team | Target Sprint | Closed Date | Days Open / to Close | Resolution Notes | Linked RAID / Control
DEF-01 | TC-002 | BR-01 | US-006 | Inbox loses sort order after page 2 | When paging beyond 50 disputes, results revert to default order instead of due-date sort. | Medium | Closed | 2026-08-14 | QA Analyst | Portal Squad | Sprint 3 | 2026-08-20 | 6 | Sort parameter now passed to paged requests; TC-002 passed on retest.
DEF-02 | TC-009 | BR-02 | US-001 | Session doesn't expire on dispute detail page | After a background token refresh, idle users on the dispute detail page stay signed in beyond 15 minutes. | High | Open | 2026-09-08 | QA Analyst | Portal Squad | Sprint 5 |  | 2 |  | CTL-05
DEF-03 | TC-029 | BR-06 | US-020 | IN_REVIEW status variant maps to Closed | Sandbox status IN_REVIEW is mapped to internal status 'Closed' instead of 'Under review', so merchants could see an open dispute as closed. | High | In Progress | 2026-09-09 | QA Analyst | Integration Squad | Sprint 4 |  | 1 | Fix in progress as part of US-020 review. | I-01
DEF-04 | TC-003 | BR-01 | US-008 | Due date filter excludes end date | Disputes due on the last day of the selected range are not returned by the filter. | Medium | Closed | 2026-08-26 | QA Analyst | Portal Squad | Sprint 3 | 2026-08-27 | 1 | Date range filter changed to include end date; TC-003 passed on retest.
Formulas:
Days Open / to Close = IF(OR([Defect ID]="",[Raised Date]=""),"",IF([Closed Date]<>"",[Closed Date]-[Raised Date],TODAY()-[Raised Date]))