## Cover
Product Roadmap
Merchant Payment Operations & Dispute Hub
Document | Outcome-based product roadmap, July 2026 to December 2028
Version | 1.1
Reporting date | 2026-09-11
Prepared by | Bhawna, Product Owner
Review cadence | Quarterly roadmap review with the Business Sponsor; refreshed at every go / no-go gate
Companion documents | PRD, Product Backlog, Change Log, RAID Log, KPI Definitions, Business Case & GTM and Post-Launch Plan
Project type | Simulation / portfolio project prepared to demonstrate Product Owner practice. Not an actual client system; dates and initiatives are illustrative.
Purpose
Shows where the Dispute Hub is going and why: the outcomes each theme should achieve, the initiatives planned to get there, how confident we are, and the gates that decide what happens next. Near-term work is committed and dated; later work is directional and will change as pilot and rollout results come in.
How to read the roadmap
Horizon | Meaning
Now | In progress, or starting within about four months of the reporting date. Scope and dates are committed.
Next | Starting within the next 12 months. Scope is planned; dates can move with gate results.
Later | More than 12 months away. Direction only: problems worth solving, not promises.
Status and colors
Status | Meaning
Done | Delivered and accepted.
In progress | Being worked on now.
Committed | Funded, scoped and scheduled.
Planned | Intended and sized, but not yet started or fully funded.
Exploring | In discovery; scope and value still being validated.
Idea | Worth investigating; no commitment.
Pending decision | Waiting on a change request or steering committee decision.
Roadmap principles
1. Every initiative serves a theme outcome and names the KPI it should move.
2. Dates get less precise the further out they are. Confidence is shown for every item.
3. Changes to Now or committed items go through change control (Change Log). Next and Later items change at the quarterly review.
4. Rollout waves and Phase 2 investments start only when their gate criteria are met.
5. New ideas enter as Idea or Exploring and need evidence before becoming Planned.
How to maintain
Edit initiatives, dates and status on the Initiatives tab. The timeline, Now / Next / Later board and Overview update automatically.
To add an initiative, add a row on the Initiatives tab, then add its ID in a row under the right theme on the Roadmap tab.
Update the reporting date above before each review; horizons are calculated from it.
Version history
Version | Date | Author | Change summary
1.0 | 2026-09-11 | Bhawna | First roadmap: six themes, 24 initiatives and 13 milestones from build through 2028.
1.1 | 2026-09-11 | Bhawna | Added six beyond-MVP initiatives (RM-25 to RM-30) and the AI copilot model risk review milestone, from the Discovery & Decision Log. Horizons match wireframes S09 to S13.

## Overview
Roadmap Overview
Merchant Payment Operations & Dispute Hub · Simulation project
Reporting date: 11-Sep-2026
Summary
Initiatives | Now | Next | Later | In progress or committed | Pending decision | Low confidence | Ideas
30 | 6 | 15 | 9 | 6 | 1 | 14 | 9
Initiatives by theme and horizon
Theme | Now | Next | Later | Total | Owner
Launch the MVP | 3 | 0 | 0 | 3 | Product Owner
Merchant adoption and rollout | 0 | 5 | 1 | 6 | Merchant Relationship Lead
Help merchants win more disputes | 0 | 5 | 3 | 8 | Product Owner
Ops efficiency | 1 | 3 | 1 | 5 | Dispute Ops Lead
Trust, compliance and data | 2 | 2 | 0 | 4 | Compliance Lead
Expansion | 0 | 0 | 4 | 4 | Business Sponsor
Next milestones
Milestone | Date |  | Type | Owner |  | Days away
CR-05 outcome definitions decision | 2026-09-18 |  | Decision | Business Sponsor |  | 7
Steering committee: CR-01 scope and CR-06 UAT approach | 2026-09-24 |  | Decision | Steering Committee |  | 13
Penetration test (committed date) | 2026-11-13 |  | Dependency | InfoSec Lead |  | 63
Go-live go / no-go | 2026-12-04 |  | Gate | Steering Committee |  | 84
MVP go-live | 2026-12-11 |  | Launch | Product Owner |  | 91
Hypercare exit review | 2027-01-22 |  | Gate | Tech Lead |  | 133
What could change the roadmap
Change | Impact on the roadmap
Penetration test slips further (D-03) | Moves go-live and everything after it. CR-06 proposes running UAT in parallel.
Tracking plan stays blocked (I-06) | Pilot activation can't be measured, so the Wave 1 gate can't be judged on evidence.
Pilot adoption misses the 60% gate (R-04) | Wave 1 waits; adoption work moves forward and Next items, including the AI copilot pilot, shift right.
Phase 2 funding isn't approved (MS-09) | Fraud case management and the Spanish portal move to Later.
Outcome definitions not agreed (CR-05) | Reporting stories slip and value recovery (KPI-01) can't be tracked.

## Roadmap
Roadmap Timeline
Merchant Payment Operations & Dispute Hub · Simulation project · July 2026 to December 2028 · Bars and milestones update from the Initiatives and Milestones tabs
| Legend (bar color = status): | Done | In progress | Committed | Planned |  |  |  | Exploring |  |  |  | Idea |  |  |  | Pending decision |  |  |  | ◆ Milestone |  |  |  | Reporting month
[5 empty] | 2026 | [5 empty] | 2027 | [11 empty] | 2028
[5 empty] | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
ID | Initiative | Status | Start | End | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01 | 2028-02-01 | 2028-03-01 | 2028-04-01 | 2028-05-01 | 2028-06-01 | 2028-07-01 | 2028-08-01 | 2028-09-01 | 2028-10-01 | 2028-11-01 | 2028-12-01
T1 | Launch the MVP
RM-01 | MVP build (Sprints 1–8) | In progress | 2026-07-20 | 2026-11-06
RM-02 | Security, UAT and hardening (Sprints 9–10) | Committed | 2026-11-09 | 2026-12-04
RM-03 | Go-live and hypercare | Committed | 2026-12-11 | 2027-01-22
T2 | Merchant adoption and rollout
RM-07 | Pilot with 10 merchants | Committed | 2027-01-11 | 2027-03-05
RM-08 | Pilot feedback fixes | Planned | 2027-02-08 | 2027-03-26
RM-10 | Wave 1 rollout | Planned | 2027-03-15 | 2027-05-28
RM-15 | Wave 2 rollout | Planned | 2027-06-07 | 2027-09-24
RM-16 | Spanish language portal | Planned | 2027-07-05 | 2027-09-24
RM-18 | General availability | Planned | 2027-10-04 | 2027-12-17
T3 | Help merchants win more disputes
RM-11 | Evidence guidance for recurring billing and travel | Planned | 2027-04-05 | 2027-05-28
RM-12 | Evidence templates by reason code | Exploring | 2027-04-05 | 2027-06-25
RM-14 | SMS deadline reminders | Idea | 2027-04-05 | 2027-06-25
RM-22 | Evidence quality checks before submission | Idea | 2028-04-03 | 2028-06-30
RM-25 | Pre-dispute alerts and early refunds | Exploring | 2027-07-05 | 2027-09-24
RM-26 | AI evidence copilot (pilot) | Exploring | 2027-07-05 | 2027-12-17
RM-27 | Friendly fraud evidence automation | Idea | 2028-01-03 | 2028-03-31
RM-29 | Root-cause insights and recommendations | Idea | 2028-01-03 | 2028-06-30
T4 | Ops efficiency
RM-06 | Fraud case reference on disputes | Pending decision | 2026-10-26 | 2026-11-06
RM-13 | Reason code admin screen | Planned | 2027-04-05 | 2027-06-25
RM-17 | Fraud case management in the hub | Exploring | 2027-07-05 | 2027-12-17
RM-19 | Retire email dispute intake | Planned | 2027-03-15 | 2027-12-17
RM-20 | Auto-accept rules for low-value disputes | Idea | 2027-10-04 | 2027-12-17
T5 | Trust, compliance and data
RM-04 | Agree dispute outcome definitions | In progress | 2026-09-07 | 2026-09-18
RM-05 | Analytics tracking plan and instrumentation | In progress | 2026-09-08 | 2026-11-20
RM-09 | Merchant satisfaction survey | Planned | 2027-01-11 | 2027-03-26
RM-28 | Dispute ratio health alerts | Exploring | 2027-04-05 | 2027-06-25
T6 | Expansion
RM-21 | Marketplace sub-merchant model | Idea | 2028-01-03 | 2028-06-30
RM-23 | Dispute API for enterprise merchants | Idea | 2028-07-03 | 2028-12-29
RM-24 | Premium dispute management service | Idea | 2028-07-03 | 2028-12-29
RM-30 | AI agent purchase readiness | Idea | 2028-04-03 | 2028-09-29
Key milestones and gates
MS-01 | CR-05 outcome definitions decision | Decision | 2026-09-18 |  |  |  | ◆
MS-02 | Steering committee: CR-01 scope and CR-06 UAT approach | Decision | 2026-09-24 |  |  |  | ◆
MS-03 | Penetration test (committed date) | Dependency | 2026-11-13 | [5 empty] | ◆
MS-04 | Go-live go / no-go | Gate | 2026-12-04 | [6 empty] | ◆
MS-05 | MVP go-live | Launch | 2026-12-11 | [6 empty] | ◆
MS-06 | Hypercare exit review | Gate | 2027-01-22 | [7 empty] | ◆
MS-07 | Pilot exit review and Wave 1 go / no-go | Gate | 2027-03-11 | [9 empty] | ◆
MS-08 | Post-implementation review | Review | 2027-04-15 | [10 empty] | ◆
MS-09 | Phase 2 funding decision | Decision | 2027-05-27 | [11 empty] | ◆
MS-10 | Wave 2 go / no-go | Gate | 2027-06-03 | [12 empty] | ◆
MS-11 | AI copilot model risk review | Decision | 2027-06-17 | [12 empty] | ◆
MS-12 | General availability go / no-go | Gate | 2027-09-30 | [15 empty] | ◆
MS-13 | 2028 roadmap planning | Review | 2027-11-30 | [17 empty] | ◆
MS-14 | Year 1 benefits review | Review | 2028-01-27 | [19 empty] | ◆
To add an initiative: add it on the Initiatives tab, then type its ID in column A of a new row under the right theme here and copy the row formatting.

## Now-Next-Later
Now, Next, Later
Outcome view of the roadmap for stakeholder conversations · Ordered by start date
Reporting date: 11-Sep-2026
| Now (6) | Next (15) | Later (9)
| Committed scope. In progress or starting within about four months. | Planned. Starting within 12 months; dates move with gate results. | Direction only. Problems worth solving later.
| MVP build (Sprints 1–8) Launch the MVP, Q3 2026 to Q4 2026 In progress, High confidence | Pilot with 10 merchants Merchant adoption and rollout, Q1 2027 Committed, Medium confidence | General availability Merchant adoption and rollout, Q4 2027 Planned, Medium confidence
| Agree dispute outcome definitions Trust, compliance and data, Q3 2026 In progress, Medium confidence | Merchant satisfaction survey Trust, compliance and data, Q1 2027 Planned, High confidence | Auto-accept rules for low-value disputes Ops efficiency, Q4 2027 Idea, Low confidence
| Analytics tracking plan and instrumentation Trust, compliance and data, Q3 2026 to Q4 2026 In progress, Low confidence | Pilot feedback fixes Merchant adoption and rollout, Q1 2027 Planned, Medium confidence | Marketplace sub-merchant model Expansion, Q1 2028 to Q2 2028 Idea, Low confidence
| Fraud case reference on disputes Ops efficiency, Q4 2026 Pending decision, Low confidence | Wave 1 rollout Merchant adoption and rollout, Q1 2027 to Q2 2027 Planned, Medium confidence | Friendly fraud evidence automation Help merchants win more disputes, Q1 2028 Idea, Low confidence
| Security, UAT and hardening (Sprints 9–10) Launch the MVP, Q4 2026 Committed, Medium confidence | Retire email dispute intake Ops efficiency, Q1 2027 to Q4 2027 Planned, Medium confidence | Root-cause insights and recommendations Help merchants win more disputes, Q1 2028 to Q2 2028 Idea, Low confidence
| Go-live and hypercare Launch the MVP, Q4 2026 to Q1 2027 Committed, Medium confidence | Evidence guidance for recurring billing and travel Help merchants win more disputes, Q2 2027 Planned, Medium confidence | Evidence quality checks before submission Help merchants win more disputes, Q2 2028 Idea, Low confidence
|  | Evidence templates by reason code Help merchants win more disputes, Q2 2027 Exploring, Medium confidence | AI agent purchase readiness Expansion, Q2 2028 to Q3 2028 Idea, Low confidence
|  | Reason code admin screen Ops efficiency, Q2 2027 Planned, Medium confidence | Dispute API for enterprise merchants Expansion, Q3 2028 to Q4 2028 Idea, Low confidence
|  | SMS deadline reminders Help merchants win more disputes, Q2 2027 Idea, Low confidence | Premium dispute management service Expansion, Q3 2028 to Q4 2028 Idea, Low confidence
Dispute ratio health alerts Trust, compliance and data, Q2 2027 Exploring, Medium confidence
Wave 2 rollout Merchant adoption and rollout, Q2 2027 to Q3 2027 Planned, Medium confidence
Spanish language portal Merchant adoption and rollout, Q3 2027 Planned, Low confidence
Fraud case management in the hub Ops efficiency, Q3 2027 to Q4 2027 Exploring, Low confidence
Pre-dispute alerts and early refunds Help merchants win more disputes, Q3 2027 Exploring, Medium confidence
AI evidence copilot (pilot) Help merchants win more disputes, Q3 2027 to Q4 2027 Exploring, Low confidence

## Themes & Outcomes
Themes & Outcomes
Merchant Payment Operations & Dispute Hub · Simulation project · What each theme should achieve and how it's measured
Theme ID | Theme | Outcome | How success is measured | Owner | Initiatives | Now | Next | Later | In progress or committed
T1 | Launch the MVP | Merchants and ops have a secure, stable Dispute Hub live by 11 December 2026. | Go-live on time; hypercare exit criteria met (EX-01 to EX-12) | Product Owner | 3 | 3 | 0 | 0 | 3
T2 | Merchant adoption and rollout | The portal becomes the default way merchants handle disputes. | KPI-06 portal evidence share 0% to 70%; KPI-08 pilot activation ≥ 60% | Merchant Relationship Lead | 6 | 0 | 5 | 1 | 1
T3 | Help merchants win more disputes | Merchants respond on time with evidence that wins. | KPI-03 on-time response 78% to 95%; KPI-04 missed-deadline loss 9% to 3%; KPI-01 value recovery 38% to 45% | Product Owner | 8 | 0 | 5 | 3 | 0
T4 | Ops efficiency | Dispute ops spends time on judgment, not re-keying and chasing. | KPI-05 handling time 42 to 25 minutes | Dispute Ops Lead | 5 | 1 | 3 | 1 | 0
T5 | Trust, compliance and data | Card data stays protected and everyone uses one trusted set of numbers. | KPI-16 zero card data incidents; KPI-15 reconciliation variance ≤ 0.5%; agreed outcome definitions | Compliance Lead | 4 | 2 | 2 | 0 | 2
T6 | Expansion | Reach merchant types and revenue the MVP doesn't serve yet. | Validated demand and business case before commitment | Business Sponsor | 4 | 0 | 0 | 4 | 0
| Total |  |  |  | 30 | 6 | 15 | 9 | 6

## Initiatives
Initiatives
Merchant Payment Operations & Dispute Hub · Simulation project · Source data for the timeline and board
Grey columns calculate automatically. Horizon is based on the reporting date on the Cover.
ID | Theme ID | Theme | Initiative | Problem or outcome | KPIs | Start | End | Weeks | Timeframe | Horizon | Status | Confidence | Effort | Owner | Gate or dependency | Linked items | Source | h_now | h_next | h_later
RM-01 | T1 | Launch the MVP | MVP build (Sprints 1–8) | Build the nine MVP epics: inbox, evidence submission, processor integration, reminders, settlements, reporting and ops queue. | Scope delivered (252 points) | 2026-07-20 | 2026-11-06 | 16 | Q3 2026 to Q4 2026 | Now | In progress | High | XL | Tech Lead | Sprint reviews; D-01, D-02, D-04 | EP-01 to EP-09 | Product Backlog | 2026-07-20
RM-02 | T1 | Launch the MVP | Security, UAT and hardening (Sprints 9–10) | Penetration test remediation, redaction validation, load and accessibility testing, UAT. | BR-15, BR-16, BR-17 | 2026-11-09 | 2026-12-04 | 4 | Q4 2026 | Now | Committed | Medium | L | Tech Lead | Pen test date (D-03); UAT approach (CR-06) | D-03, CR-06, CR-03 | Product Backlog | 2026-11-09
RM-03 | T1 | Launch the MVP | Go-live and hypercare | Launch on 11 December and stabilize through the holiday change freeze. | EX-01 to EX-12 | 2026-12-11 | 2027-01-22 | 6 | Q4 2026 to Q1 2027 | Now | Committed | Medium | M | Tech Lead | Go-live go / no-go (RV-01) | RV-01, RV-02 | Post-Launch Plan | 2026-12-11
RM-04 | T5 | Trust, compliance and data | Agree dispute outcome definitions | Resolve the Finance and Ops win-rate disagreement so reporting stories can be finished. | KPI-01, KPI-02 | 2026-09-07 | 2026-09-18 | 2 | Q3 2026 | Now | In progress | Medium | S | Product Owner | CR-05 decision by Business Sponsor | CR-05, I-05 | Change Log | 2026-09-07
RM-05 | T5 | Trust, compliance and data | Analytics tracking plan and instrumentation | Get the tracking plan approved and events live so pilot adoption can be measured. | KPI-08 to KPI-11 | 2026-09-08 | 2026-11-20 | 11 | Q3 2026 to Q4 2026 | Now | In progress | Low | M | Product Owner | Data governance approval (I-06) | I-06, US-034, LR-06 | RAID Log | 2026-09-08
RM-06 | T4 | Ops efficiency | Fraud case reference on disputes | Show a read-only fraud case ID and status on each dispute (CR-01 Option C). | KPI-05 | 2026-10-26 | 2026-11-06 | 2 | Q4 2026 | Now | Pending decision | Low | S | Product Owner | CR-01 steering committee decision (24 Sep); fraud service (D-07) | CR-01, US-036, D-07 | Change Log | 2026-10-26
RM-07 | T2 | Merchant adoption and rollout | Pilot with 10 merchants | Prove adoption, on-time responses and data protection with enterprise e-commerce merchants. | KPI-08, KPI-03, KPI-16 | 2027-01-11 | 2027-03-05 | 8 | Q1 2027 | Next | Committed | Medium | M | Product Owner | Terms of use (D-05); tracking plan (I-06); pilot go / no-go (LR-18) | RV-03, R-04, A-01 | Business Case & GTM |  | 2027-01-11
RM-08 | T2 | Merchant adoption and rollout | Pilot feedback fixes | Fix the usability issues pilot merchants raise. | KPI-10, KPI-18 | 2027-02-08 | 2027-03-26 | 7 | Q1 2027 | Next | Planned | Medium | S | Product Owner | Pilot exit review (RV-03) | IR-01 | Post-Launch Plan |  | 2027-02-08
RM-09 | T5 | Trust, compliance and data | Merchant satisfaction survey | Add a one-question survey when disputes close. | KPI-18 | 2027-01-11 | 2027-03-26 | 11 | Q1 2027 | Next | Planned | High | S | Product Owner | Monthly business review | IR-02, KPI-18 | Post-Launch Plan |  | 2027-01-11
RM-10 | T2 | Merchant adoption and rollout | Wave 1 rollout | Enterprise e-commerce and mid-market online retail (about 62% of dispute volume). | KPI-06, KPI-04 | 2027-03-15 | 2027-05-28 | 11 | Q1 2027 to Q2 2027 | Next | Planned | Medium | M | Merchant Relationship Lead | Pilot exit gates met (RV-03) | Rollout Plan Phase 2 | Business Case & GTM |  | 2027-03-15
RM-11 | T3 | Help merchants win more disputes | Evidence guidance for recurring billing and travel | Segment playbooks so Wave 2 merchants know what evidence wins. | KPI-01, KPI-06 | 2027-04-05 | 2027-05-28 | 8 | Q2 2027 | Next | Planned | Medium | S | Merchant Relationship Lead | Must be ready before Wave 2 (RV-06) | IR-08 | Post-Launch Plan |  | 2027-04-05
RM-12 | T3 | Help merchants win more disputes | Evidence templates by reason code | Guided checklists and templates for each reason code. | KPI-01, KPI-02 | 2027-04-05 | 2027-06-25 | 12 | Q2 2027 | Next | Exploring | Medium | M | Product Owner | Discovery findings at post-implementation review (RV-04) | IR-03, US-007 | Post-Launch Plan |  | 2027-04-05
RM-13 | T4 | Ops efficiency | Reason code admin screen | Let dispute ops update reason codes and response windows without engineering (CR-02 Option C). | KPI-05 | 2027-04-05 | 2027-06-25 | 12 | Q2 2027 | Next | Planned | Medium | M | Dispute Ops Lead | Quarterly roadmap review | CR-02, IR-04, US-047 | Change Log |  | 2027-04-05
RM-14 | T3 | Help merchants win more disputes | SMS deadline reminders | Reach merchant users on their phones when a deadline is close. | KPI-03, KPI-04 | 2027-04-05 | 2027-06-25 | 12 | Q2 2027 | Next | Idea | Low | M | Product Owner | CR-09 assessment and decision | CR-09, IR-05, US-027 | Change Log |  | 2027-04-05
RM-15 | T2 | Merchant adoption and rollout | Wave 2 rollout | Subscription and digital services; travel and hospitality. | KPI-06, KPI-05 | 2027-06-07 | 2027-09-24 | 16 | Q2 2027 to Q3 2027 | Next | Planned | Medium | M | Merchant Relationship Lead | Wave 1 exit gates met (RV-06) | Rollout Plan Phase 3 | Business Case & GTM |  | 2027-06-07
RM-16 | T2 | Merchant adoption and rollout | Spanish language portal | Serve Spanish-speaking merchants without a PDF workaround (CR-04 Phase 2). | KPI-06 | 2027-07-05 | 2027-09-24 | 12 | Q3 2027 | Next | Planned | Low | L | Merchant Relationship Lead | Phase 2 funding decision | CR-04, IR-07, US-046 | Change Log |  | 2027-07-05
RM-17 | T4 | Ops efficiency | Fraud case management in the hub | Let analysts work linked fraud cases and disputes together (CR-01 Phase 2). | KPI-05 | 2027-07-05 | 2027-12-17 | 24 | Q3 2027 to Q4 2027 | Next | Exploring | Low | XL | Fraud Operations Lead | Phase 2 funding decision; fraud case service (D-07) | CR-01, IR-06, US-045 | Change Log |  | 2027-07-05
RM-18 | T2 | Merchant adoption and rollout | General availability | Self-serve launch to all remaining merchants. | KPI-06, KPI-07 | 2027-10-04 | 2027-12-17 | 11 | Q4 2027 | Later | Planned | Medium | M | Product Owner | Wave 2 exit gates met (RV-08) | Rollout Plan Phase 4 | Business Case & GTM |  |  | 2027-10-04
RM-19 | T4 | Ops efficiency | Retire email dispute intake | Close the parallel email channel wave by wave once portal share targets are met. | KPI-05, KPI-06 | 2027-03-15 | 2027-12-17 | 40 | Q1 2027 to Q4 2027 | Next | Planned | Medium | M | Dispute Ops Lead | Wave exit gates; ops capacity plan (LR-17) | IR-12, BAU Transition | Post-Launch Plan |  | 2027-03-15
RM-20 | T4 | Ops efficiency | Auto-accept rules for low-value disputes | Let merchants set rules to accept disputes not worth contesting. | KPI-05 | 2027-10-04 | 2027-12-17 | 11 | Q4 2027 | Later | Idea | Low | M | Product Owner | Post-implementation review (RV-04) | IR-09 | Post-Launch Plan |  |  | 2027-10-04
RM-21 | T6 | Expansion | Marketplace sub-merchant model | Let marketplaces manage disputes for their sub-merchants. | KPI-06 | 2028-01-03 | 2028-06-30 | 26 | Q1 2028 to Q2 2028 | Later | Idea | Low | XL | Product Owner | 2028 planning | IR-10 | Business Case & GTM |  |  | 2028-01-03
RM-22 | T3 | Help merchants win more disputes | Evidence quality checks before submission | Flag weak or missing evidence before a merchant submits. | KPI-01, KPI-02 | 2028-04-03 | 2028-06-30 | 13 | Q2 2028 | Later | Idea | Low | L | Product Owner | 2028 planning | IR-11 | Post-Launch Plan |  |  | 2028-04-03
RM-23 | T6 | Expansion | Dispute API for enterprise merchants | Let large merchants connect their own order and support systems to the hub. New idea; demand not yet validated. | KPI-06, KPI-05 | 2028-07-03 | 2028-12-29 | 26 | Q3 2028 to Q4 2028 | Later | Idea | Low | L | Product Owner | Enterprise merchant interviews; 2028 planning |  | New idea |  |  | 2028-07-03
RM-24 | T6 | Expansion | Premium dispute management service | Paid assisted dispute handling for high-volume merchants. New idea; needs a business case. | Revenue (new) | 2028-07-03 | 2028-12-29 | 26 | Q3 2028 to Q4 2028 | Later | Idea | Low | L | Business Sponsor | Business case and pricing review |  | New idea |  |  | 2028-07-03
RM-25 | T3 | Help merchants win more disputes | Pre-dispute alerts and early refunds | Resolve eligible disputes before they become chargebacks using network and issuer alert programs, such as Amex Accelerated Dispute Resolution. | KPI-19, KPI-04 | 2027-07-05 | 2027-09-24 | 12 | Q3 2027 | Next | Exploring | Medium | M | Dispute Ops Lead | Alert programs and costs confirmed with acquirer; Wave 1 exit (RV-06) | S09, DSC-09 | Discovery log |  | 2027-07-05
RM-26 | T3 | Help merchants win more disputes | AI evidence copilot (pilot) | Draft evidence packets from connected systems with a win likelihood, and require human review above a set amount. | KPI-20, KPI-01, KPI-05 | 2027-07-05 | 2027-12-17 | 24 | Q3 2027 to Q4 2027 | Next | Exploring | Low | L | Product Owner | AI model risk review (MS-11); evidence templates in place (RM-12) | S10, DSC-07, DSC-08 | Discovery log |  | 2027-07-05
RM-27 | T3 | Help merchants win more disputes | Friendly fraud evidence automation | Find earlier undisputed purchases with matching identifiers to meet network rules such as Visa Compelling Evidence 3.0 and Mastercard First-Party Trust. | KPI-02, KPI-01 | 2028-01-03 | 2028-03-31 | 13 | Q1 2028 | Later | Idea | Low | M | Product Owner | Network eligibility rules confirmed; 2028 planning | S10, DSC-14 | Discovery log |  |  | 2028-01-03
RM-28 | T5 | Trust, compliance and data | Dispute ratio health alerts | Show merchants how close they are to card network monitoring thresholds and alert them before they cross. | KPI-21 | 2027-04-05 | 2027-06-25 | 12 | Q2 2027 | Next | Exploring | Medium | M | Merchant Relationship Lead | Ratio data source and thresholds confirmed with acquirer | S11, DSC-10 | Discovery log |  | 2027-04-05
RM-29 | T3 | Help merchants win more disputes | Root-cause insights and recommendations | Show which products, billing names and channels create disputes, with recommended fixes merchants can act on. | KPI-04, KPI-01 | 2028-01-03 | 2028-06-30 | 26 | Q1 2028 to Q2 2028 | Later | Idea | Low | L | Product Owner | Minimum data volume reached; 2028 planning | S12, DSC-11 | Discovery log |  |  | 2028-01-03
RM-30 | T6 | Expansion | AI agent purchase readiness | Capture AI shopping agent authorization records so merchants can defend agent-initiated purchases. | KPI-21, KPI-02 | 2028-04-03 | 2028-09-29 | 26 | Q2 2028 to Q3 2028 | Later | Idea | Low | L | Tech Lead | Network agent token standards mature; 2028 planning | S13, DSC-15 | Discovery log |  |  | 2028-04-03
Formulas:
h_now = IF([Horizon]="Now",[Start]+ROW()/100000,"")
h_next = IF([Horizon]="Next",[Start]+ROW()/100000,"")
h_later = IF([Horizon]="Later",[Start]+ROW()/100000,"")

## Milestones
Milestones & Gates
Merchant Payment Operations & Dispute Hub · Simulation project · Decisions, gates and launches that shape the roadmap
ID | Milestone | Date | Type | Owner | Linked items | Days from reporting date | Timing | h
MS-01 | CR-05 outcome definitions decision | 2026-09-18 | Decision | Business Sponsor | CR-05 | 7 | Upcoming | 2026-09-18
MS-02 | Steering committee: CR-01 scope and CR-06 UAT approach | 2026-09-24 | Decision | Steering Committee | CR-01, CR-06 | 13 | Upcoming | 2026-09-24
MS-03 | Penetration test (committed date) | 2026-11-13 | Dependency | InfoSec Lead | D-03 | 63 | Upcoming | 2026-11-13
MS-04 | Go-live go / no-go | 2026-12-04 | Gate | Steering Committee | RV-01 | 84 | Upcoming | 2026-12-04
MS-05 | MVP go-live | 2026-12-11 | Launch | Product Owner | RM-03 | 91 | Upcoming | 2026-12-11
MS-06 | Hypercare exit review | 2027-01-22 | Gate | Tech Lead | RV-02 | 133 | Upcoming | 2027-01-22
MS-07 | Pilot exit review and Wave 1 go / no-go | 2027-03-11 | Gate | Steering Committee | RV-03 | 181 | Upcoming | 2027-03-11
MS-08 | Post-implementation review | 2027-04-15 | Review | Business Sponsor | RV-04 | 216 | Upcoming | 2027-04-15
MS-09 | Phase 2 funding decision | 2027-05-27 | Decision | Steering Committee | RM-16, RM-17 | 258 | Upcoming | 2027-05-27
MS-10 | Wave 2 go / no-go | 2027-06-03 | Gate | Steering Committee | RV-06 | 265 | Upcoming | 2027-06-03
MS-11 | AI copilot model risk review | 2027-06-17 | Decision | Compliance Lead | RM-26, DSC-08 | 279 | Upcoming | 2027-06-17
MS-12 | General availability go / no-go | 2027-09-30 | Gate | Steering Committee | RV-08 | 384 | Upcoming | 2027-09-30
MS-13 | 2028 roadmap planning | 2027-11-30 | Review | Product Owner | RM-21 to RM-24 | 445 | Upcoming | 2027-11-30
MS-14 | Year 1 benefits review | 2028-01-27 | Review | Business Sponsor | RV-10 | 503 | Upcoming | 2028-01-27
Formulas:
h = IF(AND([Date]<>"",N([Days from reporting date])>=0),[Date]+ROW()/100000,"")