## Cover
RAID Log
Merchant Payment Operations & Dispute Hub
Document | Risks, Assumptions, Issues & Dependencies Log
Version | 1.0
Reporting date | 2026-09-10
Project phase | MVP build (illustrative timeline)
Prepared by | Bhawna, Product Owner
Review cadence | Weekly in project status meeting; top items to steering committee fortnightly
Project type | Simulation / portfolio project prepared to demonstrate Product Owner practice. Not an actual client system; teams, dates and vendors are illustrative.
Purpose
This log tracks the items that could affect delivery of the Merchant Payment Operations & Dispute Hub MVP. It gives leadership a single view of exposure, the owner of each item, and where decisions or support are needed. The Dashboard tab summarizes the log; the four detail tabs hold the full records.
Definitions
Type | Meaning
Risk | A future, uncertain event that would affect scope, time, cost, quality or compliance if it happened.
Assumption | Something the plan treats as true that has not yet been verified. Each one has a validation owner and date.
Issue | A problem that is happening now and needs action. A risk that materializes is moved to the Issues tab.
Dependency | A deliverable the project needs from another team or vendor (inbound), or that another team needs from the project (outbound).
Risk scoring
Score = Probability × Impact (1–25). Rating: High 15–25 · Medium 8–14 · Low 1–7. High risks need an active mitigation plan and are reported to the steering committee.
Score | Probability |  | Impact
1 | Rare | Less than 10% | Negligible | No noticeable effect on delivery
2 | Unlikely | 10–30% | Minor | Slip under 1 week; absorbed within a sprint
3 | Possible | 30–50% | Moderate | 1–2 sprint slip or a feature descoped
4 | Likely | 50–80% | Major | Milestone or go-live slip; compliance finding
5 | Almost certain | More than 80% | Severe | Regulatory breach, financial loss, or go-live blocked
Status definitions
Tab | Status values
Risks | Open · Monitoring (mitigations in place, watching triggers) · Occurred - moved to Issue · Closed
Assumptions | Unvalidated · Validating · Confirmed · Invalid - raised as Risk/Issue
Issues | Open · In Progress · Escalated · Resolved · Closed. Priority: Critical · High · Medium · Low
Dependencies | Not Started · On Track · At Risk · Late · Delivered
How to maintain this log
1. Add new items in the next empty row of the relevant tab. IDs follow R-##, A-##, I-##, D-##.
2. Fill the white columns only. Grey columns (score, rating, days open, slippage) calculate automatically.
3. Every item needs exactly one owner and a target date.
4. Update the Status and Last Updated columns at each weekly review. Close items with notes rather than deleting them.
5. When a risk occurs, set its status to 'Occurred - moved to Issue' and log a linked issue.
Version history
Version | Date | Author | Change summary
1.0 | 10-Sep-2026 | Bhawna | Initial baseline from RAID workshop and discovery outputs.

## Dashboard
RAID Dashboard
Merchant Payment Operations & Dispute Hub · Simulation project · Figures update automatically from the detail tabs
Reporting date: | 2026-09-10
Summary
Log | Total logged | Open | Needs attention |  | Needs attention means
Risks | 10 | 10 | 3 |  | Open or monitoring risks rated High (score 15+)
Assumptions | 7 | 6 | 0 |  | Validation overdue, or proven invalid
Issues | 7 | 6 | 2 |  | Escalated, or Critical and unresolved
Dependencies | 7 | 7 | 3 |  | At risk or late
Top 5 open risks by score
ID | Risk | Score | Rating | Owner | Target date | Status | Linked
R-04 | Low merchant adoption of self-service portal | 16 | High | Product Owner | 2026-11-20 | Open | A-01, I-06
R-02 | Cardholder data in merchant evidence uploads | 15 | High | Tech Lead | 2026-10-15 | Open | D-03
R-03 | Missed dispute response deadlines due to status sync lag | 15 | High | Tech Lead | 2026-11-06 | Open | A-02, D-01
R-01 | Card network dispute rule changes before go-live | 12 | Medium | Product Owner | 2026-10-30 | Open | I-02
R-05 | Legacy settlement data quality affects reports | 12 | Medium | Data Engineering Lead | 2026-10-23 | Monitoring | D-04, A-06
Risk heat map (count of open and monitoring risks)
| Probability ↓ Impact → | 1 · Negligible | 2 · Minor | 3 · Moderate | 4 · Major | 5 · Severe
| 5 · Almost certain | 0 | 0 | 0 | 0 | 0 |  | High
| 4 · Likely | 0 | 0 | 2 | 1 | 0 |  | Medium
| 3 · Possible | 0 | 0 | 1 | 1 | 2 |  | Low
| 2 · Unlikely | 0 | 0 | 1 | 2 | 0
| 1 · Rare | 0 | 0 | 0 | 0 | 0
Support requested from leadership
# | Ask |  |  |  |  | Related items | Needed by
1 | Help secure an InfoSec penetration test slot before UAT. The currently committed date is two weeks after the date needed. |  |  |  |  | D-03, R-02 | 2026-09-25
2 | Broker a decision between Finance and Dispute Ops on how 'won' and 'lost' disputes are defined, so the win-rate KPI can be finalized. |  |  |  |  | I-05 | 2026-09-18
3 | Confirm the MVP scope baseline and agree to defer fraud case management and dispute-to-fraud linking to Phase 2. |  |  |  |  | R-07, D-07 | 2026-09-25

## Risks
Risk Register
Merchant Payment Operations & Dispute Hub · Simulation project
Grey columns calculate automatically. Edit white columns only. Use the dropdowns where provided.
ID | Category | Risk Title | Description (cause → event → effect) | Raised By | Date Raised | Owner | Probability (1-5) | Impact (1-5) | Score | Rating | Response Strategy | Mitigation Plan | Contingency Plan | Trigger / Early Warning | Target Date | Status | Linked Items | Last Updated | Rank helper
R-01 | Compliance & Regulatory | Card network dispute rule changes before go-live | Card networks periodically update dispute reason codes and response time frames. If a rule change lands during build, reason-code mapping and SLA timers could be wrong at launch, causing lost disputes and rework. | Product Owner | 2026-08-18 | Product Owner | 3 | 4 | 12 | Medium | Mitigate | Hold reason codes and response windows as configurable reference data rather than hard-coded logic; subscribe to network bulletins; add a rule-change check to sprint planning. | Apply configuration update and notify merchants within 5 business days of the rule effective date. | New network bulletin affecting dispute codes or time frames. | 2026-10-30 | Open | I-02 | 2026-09-10 | 12.0099
R-02 | Security & Data Privacy | Cardholder data in merchant evidence uploads | Merchants may upload receipts, invoices or screenshots that show full card numbers. If unmasked card numbers are stored, the evidence repository enters PCI DSS scope, triggering remediation work and possible audit findings. | Compliance Lead | 2026-08-18 | Tech Lead | 3 | 5 | 15 | High | Mitigate | Add upload guidance and file-type limits; run automated card-number detection and redaction on upload; confirm storage design with InfoSec. | Quarantine flagged files and ask the merchant to resubmit redacted evidence. | Card-number detection hits during UAT test uploads; InfoSec design review comments. | 2026-10-15 | Open | D-03 | 2026-09-10 | 15.0099
R-03 | Operations | Missed dispute response deadlines due to status sync lag | Dispute status and due dates come from the processor feed. If the feed is delayed or fails silently, merchants see stale deadlines and miss response windows, leading to automatic chargeback losses and complaints. | Dispute Ops Lead | 2026-08-25 | Tech Lead | 3 | 5 | 15 | High | Mitigate | Monitor feed freshness with alerts after 2 hours without updates; show a 'last synced' timestamp in the portal; send deadline reminders at 5 and 2 days before due date. | Ops team contacts affected merchants directly; request deadline extensions where network rules allow. | Feed latency above 2 hours; spike in 'deadline passed' statuses. | 2026-11-06 | Open | A-02, D-01 | 2026-09-10 | 15.0099
R-04 | Adoption & Change | Low merchant adoption of self-service portal | Merchants currently handle disputes by email and phone. If they don't switch to the portal, manual ops workload stays flat and the business case (lower handling time per dispute) is not realized. | Product Owner | 2026-08-25 | Product Owner | 4 | 4 | 16 | High | Mitigate | Pilot with 10 high-volume merchants; in-portal onboarding guide; track activation and evidence-submission rate in Amplitude; phase out email intake after the pilot. | Extend the pilot and add assisted onboarding through relationship managers. | Pilot activation below 60% after 4 weeks. | 2026-11-20 | Open | A-01, I-06 | 2026-09-10 | 16.0099
R-05 | Data | Legacy settlement data quality affects reports | Settlement and chargeback data from legacy systems has gaps such as missing merchant IDs and duplicate records. If not cleansed, Power BI reports will show reconciliation mismatches and stakeholders will lose trust in the dashboards. | Data Analyst | 2026-09-01 | Data Engineering Lead | 4 | 3 | 12 | Medium | Mitigate | Profile source data; define data quality rules and an exception report; reconcile a sample month against the finance ledger before report sign-off. | Label affected metrics as provisional and release reports in phases. | Reconciliation variance above 0.5% in the sample month. | 2026-10-23 | Monitoring | D-04, A-06 | 2026-09-10 | 12.0099
R-06 | Resourcing | Limited SME availability during Q4 peak | Dispute ops SMEs are needed for process design and UAT, but the Q4 holiday season drives peak dispute volumes. If SMEs are pulled into business-as-usual work, UAT may slip past the planned window. | Project Manager | 2026-09-01 | Project Manager | 3 | 3 | 9 | Medium | Mitigate | Book SME time for UAT now; record process walkthroughs early; nominate backup SMEs. | Run UAT in shorter focused sessions or move remaining UAT to early January. | SME attendance below 50% in two consecutive sessions. | 2026-10-02 | Open | A-05 | 2026-09-10 | 9.0099
R-07 | Scope | Scope creep from fraud case management requests | Stakeholders have asked to add fraud case management to the hub. If accepted into the MVP without trade-offs, sprint capacity will be exceeded and the go-live date will slip. | Product Owner | 2026-09-03 | Product Owner | 4 | 3 | 12 | Medium | Avoid | Log requests in the backlog as Phase 2 candidates; apply change control with an impact assessment; agree the MVP scope baseline with the sponsor. | Descope lower-priority MVP stories if a fraud feature is mandated. | New feature requests raised outside backlog refinement. | 2026-09-25 | Open | D-07, A-04 | 2026-09-10 | 12.0099
R-08 | Third Party | Vendor security assessment delay for evidence storage | The document storage vendor must pass a third-party risk assessment before production use. If the assessment runs long, evidence upload cannot go live. | Tech Lead | 2026-09-03 | Vendor Manager | 2 | 4 | 8 | Medium | Mitigate | Submit the vendor questionnaire early; request the vendor's SOC 2 report up front; identify approved internal storage as a fallback. | Launch on approved internal storage and migrate later. | Assessment not started 6 weeks before go-live. | 2026-10-09 | Open |  | 2026-09-10 | 8.0099
R-09 | Quality | Portal performance at peak chargeback volume | Chargeback volume rises after the holiday season. If the portal and APIs are not load-tested at peak volumes, response times degrade when merchants most need the service. | Tech Lead | 2026-09-08 | QA Lead | 2 | 4 | 8 | Medium | Mitigate | Load test at 3x forecast peak; configure autoscaling; include performance targets in acceptance criteria. | Throttle non-critical reports during peak and scale infrastructure manually. | 95th percentile API response above 2 seconds in load testing. | 2026-11-13 | Open |  | 2026-09-10 | 8.0099
R-10 | Compliance & Regulatory | Accessibility gaps in merchant portal | If portal screens don't meet WCAG 2.1 AA, the client may face accessibility complaints and a post-launch remediation effort. | UX Designer | 2026-09-08 | UX Designer | 2 | 3 | 6 | Low | Mitigate | Add accessibility checks to Figma design review and the definition of done; run automated and manual audits before UAT. | Prioritize remediation stories in the first post-launch sprint. | Audit finds critical accessibility defects. | 2026-11-06 | Open |  | 2026-09-10 | 6.0099
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Assumptions
Assumptions Log
Merchant Payment Operations & Dispute Hub · Simulation project
Grey columns calculate automatically. Edit white columns only. Use the dropdowns where provided.
ID | Category | Assumption | Basis / Source | Impact if False | Raised By | Date Raised | Validation Owner | Validation Method | Validate By | Status | Overdue? | Outcome / Notes | Linked Items | Last Updated
A-01 | Adoption | Merchants will submit dispute evidence through the portal instead of email. | Discovery interviews: merchants asked for status visibility and fewer email exchanges. | Adoption and ops efficiency benefits are not met (see R-04). | Product Owner | 2026-08-18 | Product Owner | Pilot with 10 merchants; measure share of evidence submitted via the portal. | 2026-11-20 | Validating | No | Pilot merchant list agreed; onboarding in progress. | R-04 | 2026-09-10
A-02 | Technical | The processor dispute API sends near-real-time status updates through webhooks. | Processor API documentation reviewed during discovery. | A polling design is needed and the stale-deadline risk (R-03) increases. | Tech Lead | 2026-08-18 | Tech Lead | Measure webhook latency in sandbox and a production-like environment. | 2026-09-30 | Validating | No | Sandbox testing in progress; status inconsistencies logged as I-01. | R-03, I-01, D-01 | 2026-09-10
A-03 | Technical | The existing identity platform supports merchant role-based access (Admin, Finance, Operations). | IAM team confirmed the role model is already used for other merchant tools. | Custom role management must be built, adding roughly 2 sprints. | Tech Lead | 2026-08-20 | IAM Lead | Walk through role configuration with the IAM team. | 2026-09-18 | Confirmed |  | Confirmed in IAM workshop on 04-Sep-2026. | D-02 | 2026-09-10
A-04 | Scope | The MVP supports a single currency (USD) and English only. | Agreed in scope workshop to limit MVP complexity. | Multi-currency views and localization would be needed, increasing effort and timeline. | Product Owner | 2026-08-20 | Business Sponsor | Confirm at scope baseline sign-off. | 2026-09-25 | Unvalidated | No |  | R-07 | 2026-09-10
A-05 | Resourcing | Dispute ops headcount stays the same during the MVP. | Current approved budget plan. | Training plans and capacity estimates would need to change. | Project Manager | 2026-08-25 | Dispute Ops Lead | Confirm headcount plan with ops leadership. | 2026-10-02 | Unvalidated | No |  | R-06 | 2026-09-10
A-06 | Data | 12 months of historical dispute data is available for baseline KPIs. | Data team indicated archive retention covers at least 12 months. | Baseline win rate and handling time can't be measured, weakening benefits tracking. | Data Analyst | 2026-09-01 | Data Engineering Lead | Run a data availability query against the warehouse. | 2026-09-18 | Validating | No |  | R-05 | 2026-09-10
A-07 | Compliance | Dispute evidence can follow the existing records retention policy; no new policy is needed. | Similar document types are already covered by the records policy. | New retention rules would need legal review and storage design changes. | Compliance Lead | 2026-09-01 | Legal Counsel | Legal review of the retention policy against dispute evidence types. | 2026-10-09 | Validating | No |  | D-05 | 2026-09-10
Formulas:
Overdue? = IF(OR([Validate By]="",[Status]="Confirmed",[Status]="Invalid - raised as Risk/Issue"),"",IF(TODAY()>[Validate By],"Overdue","No"))

## Issues
Issues Log
Merchant Payment Operations & Dispute Hub · Simulation project
Grey columns calculate automatically. Edit white columns only. Use the dropdowns where provided.
ID | Category | Issue Title | Description | Impact on Delivery | Raised By | Date Raised | Owner | Priority | Action Plan | Target Resolution | Status | Escalated To | Days Open | Linked Items | Resolution Notes | Last Updated
I-01 | Technical | Sandbox returns inconsistent dispute status values | The processor sandbox returns different status values for the same dispute stage (for example UNDER_REVIEW and IN_REVIEW). | Integration testing of status-tracking stories in Sprint 4 is blocked. | QA Lead | 2026-09-02 | Tech Lead | High | Vendor ticket raised; build a status normalization layer; stub responses to unblock testing. | 2026-09-16 | In Progress |  | 8 | A-02, D-01 |  | 2026-09-10
I-02 | Data | Unmapped dispute reason codes | 14 reason codes in the mapping table have no internal category, so these disputes can't be routed or reported correctly. | Routing logic and reason-code reporting are incomplete; Sprint 4 story acceptance at risk. | Business Analyst | 2026-09-03 | Business Analyst | High | Mapping workshop with dispute ops; route unmapped codes to a manual review queue in the meantime. | 2026-09-17 | Open |  | 7 | R-01 |  | 2026-09-10
I-03 | Design | Figma MVP screens awaiting merchant ops sign-off | Evidence upload and dispute detail screens have been awaiting stakeholder review for two weeks. | Sprint 5 refinement is blocked; development risks starting on unapproved designs. | UX Designer | 2026-08-28 | Product Owner | Medium | Time-boxed 45-minute review booked; escalated to sponsor for sign-off by target date. | 2026-09-15 | Escalated | Business Sponsor | 13 |  |  | 2026-09-10
I-04 | Environment | Test environment lacks masked production-like data | The UAT environment has only synthetic data that doesn't reflect real dispute patterns. | Edge cases such as partial refunds and second-cycle disputes can't be tested. | QA Lead | 2026-09-04 | Data Engineering Lead | Medium | Request a masked data extract; build a targeted synthetic data set for edge cases in the meantime. | 2026-09-30 | Open |  | 6 |  |  | 2026-09-10
I-05 | Business Rules | No agreed definition of dispute 'won' and 'lost' | Finance counts partially reversed disputes as lost; dispute ops counts them as won. | The win-rate KPI in Power BI can't be finalized; reporting story acceptance criteria remain open. | Business Analyst | 2026-09-07 | Product Owner | High | Decision meeting with finance and ops leads; record the agreed definition in the data dictionary. | 2026-09-18 | Escalated | Business Sponsor | 3 |  |  | 2026-09-10
I-06 | Governance | Analytics tracking plan awaiting data governance approval | The Amplitude event tracking plan for the portal has not yet been approved by data governance. | Product analytics can't be instrumented; pilot adoption measurement (R-04) at risk. | Product Analyst | 2026-09-08 | Product Owner | Medium | Submit plan for privacy review; remove merchant-identifying event properties that aren't required. | 2026-09-22 | Open |  | 2 | R-04 |  | 2026-09-10
I-07 | Access | New vendor engineers lacked Jira and Confluence access | Two vendor engineers could not access the backlog or documentation in their first week. | Lost onboarding time in Sprint 3. | Scrum Master | 2026-08-24 | Project Manager | Low | Raised access requests with IT service desk and added access setup to the onboarding checklist. | 2026-08-28 | Closed |  |  |  | Access granted 27-Aug-2026; onboarding checklist updated. | 2026-08-28
Formulas:
Days Open = IF(OR([Date Raised]="",[Status]="Resolved",[Status]="Closed"),"",TODAY()-[Date Raised])

## Dependencies
Dependencies Log
Merchant Payment Operations & Dispute Hub · Simulation project
Grey columns calculate automatically. Edit white columns only. Use the dropdowns where provided.
ID | Direction | Dependency Title | Description | Provider (Team / Vendor) | Receiver | Project Owner | Needed By | Committed Date | Slippage (days) | Impact if Late | Criticality | Status | Mitigation / Next Step | Linked Items | Last Updated
D-01 | Inbound | Processor dispute API production access | Production credentials and allow-listing needed to connect to the processor dispute API. | Payment processor (third party) | Project team | Tech Lead | 2026-10-16 | 2026-10-23 | 7 | Go-live integration testing is compressed by one week. | High | At Risk | Weekly vendor call; request early allow-listing of test merchant IDs. | R-03, I-01 | 2026-09-10
D-02 | Inbound | Merchant roles configured in identity platform | Admin, Finance and Operations roles set up for portal users. | IAM team | Project team | Tech Lead | 2026-10-02 | 2026-09-30 | -2 | Portal login and permissions can't be tested. | High | On Track | Joint checkpoint every Tuesday. | A-03 | 2026-09-10
D-03 | Inbound | Penetration test before UAT | Security testing of the portal and evidence upload service, required before UAT sign-off. | InfoSec | Project team | Tech Lead | 2026-10-30 | 2026-11-13 | 14 | UAT start delayed; go-live security sign-off at risk. | Critical | At Risk | Requested a priority testing slot; leadership support requested (see Dashboard). | R-02 | 2026-09-10
D-04 | Inbound | Settlement data pipeline to reporting warehouse | Daily load of settlement and chargeback data into the warehouse used by Power BI. | Data Engineering | Project team | Data Analyst | 2026-10-09 | 2026-10-09 | 0 | Power BI reports can only be built and tested on sample data. | Medium | On Track | Data quality rules agreed as part of pipeline acceptance. | R-05 | 2026-09-10
D-05 | Inbound | Legal sign-off on merchant portal terms of use | Approved terms covering evidence submission and data use in the portal. | Legal & Compliance | Project team | Product Owner | 2026-10-23 |  |  | Pilot merchants can't be onboarded. | High | Not Started | Draft terms shared 08-Sep-2026; awaiting legal review slot. | A-07 | 2026-09-10
D-06 | Outbound | Dispute status API for servicing agent console | Servicing agents need dispute status to answer merchant calls without transferring to dispute ops. | Project team | Customer Servicing | Product Owner | 2026-11-27 | 2026-11-27 | 0 | Agents can't see dispute status; call handling time stays high. | Medium | On Track | API contract shared; joint review at end of Sprint 5. |  | 2026-09-10
D-07 | Inbound | Fraud case-ID service for dispute linking | Service that links a dispute to an existing fraud case. | Fraud Platform team | Project team | Product Owner | 2026-11-06 | 2026-12-11 | 35 | Dispute-to-fraud linking moves out of the MVP. | Medium | Late | Proposed deferral of linking to Phase 2; tracked in joint sync. | R-07 | 2026-09-10