## Cover
Post-Launch Plan
Merchant Payment Operations & Dispute Hub
Document | Hypercare, support model, KPI triggers, benefits tracking, iteration roadmap, BAU transition, reviews and lessons learned
Version | 1.0
Reporting date | 2026-09-10
Go-live date | 2026-12-11
Prepared by | Bhawna, Product Owner
Companion documents | RAID_Log, Change_Log, Product_Backlog, RTM, KPI_Definitions, Business_Case_GTM and Engagement_Plan workbooks
Project type | Simulation / portfolio project prepared to demonstrate Product Owner practice. Not an actual client system; all dates, targets and teams are illustrative.
Purpose
Sets out what happens after go-live so the launch turns into lasting value: how the platform is stabilized in hypercare, how incidents are handled, which KPI signals trigger action, how benefits are tracked against the business case, what the product does next, how ownership moves to business-as-usual teams, and when results are reviewed.
Post-launch lifecycle
Stage | What it covers
1. Hypercare | Go-live on 11-Dec-2026 to hypercare exit on 22-Jan-2027: intensive support, holiday change freeze, then evidenced exit criteria.
2. Operate and measure | Support tiers, severity targets and playbooks; KPI triggers reviewed daily, weekly and monthly.
3. Realize benefits | Quarterly targets that roll up to the business case; actuals entered each quarter with status calculated automatically.
4. Iterate | Roadmap of improvements from pilot feedback, KPI triggers and Phase 2 commitments, prioritized by value and effort.
5. Transition to BAU | Runbooks, dashboards, backlog and vendor ownership handed to client teams; email dispute intake retired wave by wave.
6. Review and learn | Go / no-go reviews, post-implementation review, quarterly benefits reviews and a lessons learned log.
How to maintain
1. During hypercare, enter actuals for exit criteria daily; status calculates against thresholds.
2. Each quarter, enter benefit actuals; update the business case if variance persists for two quarters.
3. Re-score roadmap items after each review; the board on the Dashboard re-orders automatically.
4. Add lessons after each review and sprint retrospective; turn each lesson into an action with an owner.
Blue text on yellow cells are inputs. Grey columns calculate automatically. Dashboard date windows use the reporting date.
Version history
Version | Date | Author | Change summary
1.0 | 2026-09-10 | Bhawna | Initial post-launch plan prepared before go-live for steering committee review.

## Dashboard
Post-Launch Dashboard
Merchant Payment Operations & Dispute Hub · Simulation project · Plan view before go-live; status fills in as actuals are entered
Reporting date: 10-Sep-2026 · Go-live: 11-Dec-2026
Summary
Days to go-live | Hypercare exit criteria met |  | KPI triggers | Roadmap: Now | Roadmap: Next | Roadmap: Later | BAU handovers accepted | Lessons captured
92 | 0 of 12 |  | 12 | 2 | 7 | 3 | 0 of 12 | 6
Hypercare timeline and exit
Phase | Start | End | Days | Lead |  | Coverage
Intensive hypercare | 2026-12-11 | 2026-12-18 | 8 | Tech Lead |  | Business hours plus on-call; squads on standby
Stabilization during change freeze | 2026-12-21 | 2027-01-08 | 19 | Project Manager |  | Reduced rota plus on-call; named holiday cover for every role
Pilot hypercare and exit readiness | 2027-01-11 | 2027-01-22 | 12 | Product Owner |  | Business hours plus on-call; handover shadowing with run team
Exit recommendation | Awaiting evidence
Benefits path: quarterly targets
Measure | 2027 Q1 | 2027 Q2 | 2027 Q3 | 2027 Q4 | 2028 Q1 | 2028 Q2 | 2028 Q3 | 2028 Q4
Portal evidence share (KPI-06) | 10% | 30% | 45% | 55% | 57% | 60% | 61% | 62%
Ops handling time per dispute (KPI-05) | 40 | 36 | 32 | 29 | 28 | 27 | 26 | 25
On-time response rate (KPI-03) | 82% | 86% | 89% | 91% | 92% | 93% | 94% | 95%
Missed-deadline loss rate (KPI-04) | 8.5% | 7% | 6% | 5% | 4.5% | 4% | 3.5% | 3%
Settlement contacts per 100 merchants (KPI-07) | 14 | 12.5 | 11 | 10 | 9.5 | 9 | 8.5 | 8
Dispute value recovery rate (KPI-01) | 38% | 39.5% | 41% | 42% | 43% | 44% | 44.5% | 45%
Iteration roadmap board (ordered by priority)
Now (2) |  |  | Next (7) |  |  | Later (3)
Pilot feedback fixes · 2027 Q1 |  |  | Recurring billing and travel evidence guidance · 2027 Q2 |  |  | Auto-accept rules for low-value disputes · 2027 Q4
Merchant satisfaction survey · 2027 Q1 |  |  | Evidence templates by reason code · 2027 Q2 |  |  | Evidence quality checks before submission · 2028 Q2
|  |  | Retire email dispute intake · 2027 Q4 |  |  | Marketplace sub-merchant model · 2028 Q1
Reason code admin screen · 2027 Q2
SMS deadline reminders · 2027 Q2
Spanish language portal · 2027 Q3
Fraud case management in the hub · 2027 Q3
Upcoming reviews
Review | Date |  | Chair |  | Decision or output |  |  | Days away
Go-live go / no-go | 2026-12-04 |  | Steering Committee |  | Go-live decision |  |  | 85
Hypercare exit review | 2027-01-22 |  | Tech Lead |  | Hypercare exit decision |  |  | 134
Pilot exit review | 2027-03-11 |  | Steering Committee |  | Wave 1 go / no-go |  |  | 182
Post-implementation review | 2027-04-15 |  | Business Sponsor |  | Improvement actions; business case refresh |  |  | 217
Quarterly benefits review (Q1) | 2027-04-22 |  | Steering Committee |  | Benefits status; corrective actions |  |  | 224
Wave 2 go / no-go | 2027-06-03 |  | Steering Committee |  | Wave 2 decision |  |  | 266
BAU handover by area
Area | Items |  | Accepted |  | In progress |  | Not started or at risk
Support | 3 |  | 0 |  | 0 |  | 3
Product | 2 |  | 0 |  | 0 |  | 2
Data | 2 |  | 0 |  | 0 |  | 2
Technology | 2 |  | 0 |  | 0 |  | 2
Knowledge | 1 |  | 0 |  | 0 |  | 1
Operations | 1 |  | 0 |  | 1 |  | 0
Commercial | 1 |  | 0 |  | 0 |  | 1

## Hypercare
Hypercare Plan
Merchant Payment Operations & Dispute Hub · Simulation project · Stabilize after go-live and exit on evidence, not on a date
Enter Actual values (blue) during hypercare. Status calculates against each threshold.
Hypercare phases
ID | Phase | Start | End | Days | Context | Rituals | Coverage | Lead
HC-P1 | Intensive hypercare | 2026-12-11 | 2026-12-18 | 8 | Go-live week with internal users and controlled traffic | Daily 09:00 and 16:00 hypercare stand-ups; engineers co-located with dispute ops; war room channel | Business hours plus on-call; squads on standby | Tech Lead
HC-P2 | Stabilization during change freeze | 2026-12-21 | 2027-01-08 | 19 | Holiday change freeze; emergency fixes only | Daily 09:00 stand-up; weekly steering update; freeze exception process for Sev 1 and Sev 2 fixes | Reduced rota plus on-call; named holiday cover for every role | Project Manager
HC-P3 | Pilot hypercare and exit readiness | 2027-01-11 | 2027-01-22 | 12 | Pilot merchants onboard; exit criteria evidenced | Daily stand-up; pilot feedback triage; hypercare exit review on 22-Jan | Business hours plus on-call; handover shadowing with run team | Product Owner
Exit criteria
ID | Criterion | Measure |  | Type | Direction | Threshold | Actual | Status | Evidence | Owner | Linked items
EX-01 | No open Sev 1 or Sev 2 incidents | Consecutive business days with zero open Sev 1 / Sev 2 |  | Numeric | ≥ | 10 |  | Not measured | Incident tool report | Tech Lead | Support & Incidents
EX-02 | Sev 3 backlog under control | Open Sev 3 incidents, all with owner and target date |  | Numeric | ≤ | 10 |  | Not measured | Incident tool report | Tech Lead
EX-03 | Status updates are current | Status sync latency p95 over last 10 business days (minutes) |  | Numeric | ≤ | 5 |  | Not measured | Status event log dashboard | Tech Lead | KPI-12, R-03
EX-04 | Processor feed reliable | Feed freshness breaches in last 2 weeks |  | Numeric | ≤ | 0 |  | Not measured | Monitoring alerts | Tech Lead | KPI-13, D-01
EX-05 | Portal performance | API response time p95 at daily peak (seconds) |  | Numeric | ≤ | 2 |  | Not measured | APM dashboard | Tech Lead | KPI-14, R-09
EX-06 | No card data exposure | Confirmed card number detections since go-live |  | Numeric | ≤ | 0 |  | Not measured | Redaction logs and DLP scans | Compliance Lead | KPI-16, CTL-01
EX-07 | Missed deadlines not caused by the platform | Disputes expired due to a platform defect |  | Numeric | ≤ | 0 |  | Not measured | Expired dispute root-cause log | Dispute Ops Lead | KPI-04
EX-08 | Monitoring alerts tuned | Share of alerts that were false positives in last 2 weeks |  | Numeric | ≤ | 10% |  | Not measured | Alert review log | Tech Lead
EX-09 | Runbooks accepted by run team | Run team signs off runbooks for top 10 incident scenarios |  | Yes/No | = | Yes |  | Not measured | Signed runbook acceptance | Run Team Lead | BAU Transition
EX-10 | Support tiers operating | L1 servicing and dispute ops resolving or routing tickets without delivery team help |  | Yes/No | = | Yes |  | Not measured | Ticket routing sample review | Servicing Lead | LR-09
EX-11 | Pilot merchants onboarded | Pilot merchants with at least one active user |  | Numeric | ≥ | 8 |  | Not measured | Amplitude activation report | Merchant Relationship Lead | KPI-08, I-06
EX-12 | Merchant-reported issues triaged | Pilot feedback items triaged into backlog within 5 business days |  | Numeric | ≥ | 95% |  | Not measured | Feedback log | Product Owner | Iteration Roadmap
| Exit criteria met | 0 of 12
| Hypercare exit recommendation | Awaiting evidence

## Support & Incidents
Support Model & Incident Management
Merchant Payment Operations & Dispute Hub · Simulation project · Severity targets, support tiers and playbooks
Severity levels and targets
Severity | Label | Examples | Response target | Resolution target | Communication | Incident lead
Sev 1 | Critical | Portal or processor integration down for all merchants; confirmed card number exposure; status feed down with deadlines at risk | 15 minutes | 4 hours to workaround or fix | Business Sponsor within 1 hour; merchant status banner; hourly updates | Incident manager (Tech Lead on call)
Sev 2 | High | Evidence submission failing for multiple merchants; reminders not sending; wrong statuses shown to merchants | 30 minutes | 1 business day | Product Owner within 2 hours; affected merchants contacted by dispute ops | Tech Lead
Sev 3 | Medium | Issue affecting a single merchant or feature with a workaround; report data delayed | 4 business hours | 5 business days | Logged in weekly status; merchant updated by servicing | Run Team Lead
Sev 4 | Low | Cosmetic issue, minor text or layout problem, enhancement request | 1 business day | Next planned release | Added to backlog; no proactive comms | Product Owner
Support tiers
Tier | Team |  | Responsibilities |  | Tools | Route onward when
L1 | Servicing agents and dispute ops analysts |  | First contact for merchants; answer how-to questions; check dispute status; log tickets |  | Knowledge base, call scripts, status API console | Route to L2 if not resolved on first contact or if more than one merchant is affected
L2 | Run team (product support) |  | Diagnose portal and data issues; manage incidents; apply configuration fixes such as reason code data |  | Runbooks, monitoring dashboards, admin tools | Route to L3 for code defects, integration faults or security events
L3 | Engineering squads and vendors |  | Fix code and integration defects; work with processor and storage vendors |  | Source code, deployment pipeline, vendor support contracts | Engage InfoSec immediately for any card data or security event
Incident playbooks
ID | Scenario | Response steps |  |  | Owner | Linked items
PB-01 | Card number found after redaction | Declare Sev 1; quarantine affected files; notify Compliance and InfoSec within 1 hour; follow the data incident process; root cause before redaction resumes for the affected file type |  |  | Compliance Lead | KPI-16, CTL-01, R-02
PB-02 | Processor feed outage | Declare Sev 1 if more than 2 hours during business hours; show stale-data banner; dispute ops contact merchants with disputes due within 2 days; request deadline extensions where network rules allow |  |  | Dispute Ops Lead | KPI-13, R-03, D-01
PB-03 | Evidence submission failures | Declare Sev 2; switch affected merchants to assisted submission by dispute ops; track deadlines manually until fixed |  |  | Tech Lead | US-015, BR-03
PB-04 | Wrong statuses shown to merchants | Declare Sev 2; hide affected status labels; correct mapping in reference data; notify affected merchants |  |  | Tech Lead | US-020, DEF-03
PB-05 | Settlement report variance | Hold settlement reports if variance exceeds 1%; label data provisional; finance and data engineering reconcile before release |  |  | Finance Lead | KPI-15, R-05

## KPI Triggers
Monitoring Cadence & KPI Triggers
Merchant Payment Operations & Dispute Hub · Simulation project · Thresholds that turn a KPI signal into a named action
KPI IDs refer to the KPI_Definitions workbook.
Review cadence
Forum |  | Frequency | Chair | KPIs and inputs |  | When
Daily hypercare stand-up |  | Daily during hypercare | Tech Lead | Incidents, KPI-12, KPI-13, KPI-14, KPI-16, pilot issues |  | Until hypercare exit
Weekly KPI review |  | Weekly | Product Owner | KPI-03, KPI-04, KPI-06, KPI-08 to KPI-11, open triggers |  | From go-live
Monthly business review |  | Monthly | Business Sponsor | All Outcome KPIs, benefits tracker, trigger actions, roadmap changes |  | From February 2027
Quarterly benefits review |  | Quarterly | Steering Committee | Benefits realization vs business case, scenario refresh, wave decisions |  | From April 2027
KPI triggers
ID | KPI | Signal | Trigger threshold | Response | Owner | Response time | Review forum
TR-01 | KPI-16 | Card data exposure incidents | Any confirmed detection | Run playbook PB-01 | Compliance Lead | Immediate | Incident process
TR-02 | KPI-13 | Feed freshness breach | No updates for 2 hours in business hours | Run playbook PB-02 | Dispute Ops Lead | Immediate | Incident process
TR-03 | KPI-12 | Status sync latency p95 | Above 10 minutes for a day | Raise Sev 2; investigate webhook backlog; enable polling fallback | Tech Lead | Same day | Daily hypercare stand-up
TR-04 | KPI-14 | API response time p95 | Above 3 seconds at daily peak | Raise Sev 2; scale infrastructure; review slow endpoints | Tech Lead | Same day | Daily hypercare stand-up
TR-05 | KPI-08 | Pilot activation rate | Below 45% at week 4 of pilot | Pilot intervention: call each inactive merchant, fix onboarding blockers, extend pilot if needed | Merchant Relationship Lead | 1 week | Weekly KPI review
TR-06 | KPI-03 | On-time response rate | Below 90% for 2 consecutive weeks | Review reminder timing and ops follow-up; check deadline accuracy | Dispute Ops Lead | 1 week | Weekly KPI review
TR-07 | KPI-10 | Evidence submission completion | Below 70% for 2 weeks | UX review of upload and submit flow using funnel drop-off and session feedback | Product Owner | 2 weeks | Weekly KPI review
TR-08 | KPI-06 | Portal evidence share | More than 10 points below the wave target | Targeted adoption campaign for the segment; RM outreach to top email senders | Merchant Relationship Lead | 2 weeks | Monthly business review
TR-09 | KPI-05 | Ops handling time | Above 32 minutes for a month | Time study on slowest dispute types; backlog items for automation | Dispute Ops Lead | 1 month | Monthly business review
TR-10 | KPI-15 | Settlement reconciliation variance | Above 1% for a month | Run playbook PB-05 | Finance Lead | Before month-end reports | Monthly business review
TR-11 | KPI-17 | Critical or serious accessibility issue | Any new issue on a live screen | Fix in next release; interim assisted support for affected users | UX Designer | Next release | Monthly business review
TR-12 | KPI-18 | Merchant satisfaction | Below 3.8 for a month | Review verbatim feedback; add top themes to Iteration Roadmap | Product Owner | 1 month | Monthly business review

## Benefits Tracker
Benefits Realization Tracker
Merchant Payment Operations & Dispute Hub · Simulation project · Quarterly KPI targets that roll up to the base business case
Targets are inputs from the base case. Enter actuals each quarter; status: On track meets target, Watch within 10%, Off track beyond 10%.
Quarterly targets (base case)
Measure | KPI | Unit | Direction | Baseline | 2027 Q1 | 2027 Q2 | 2027 Q3 | 2027 Q4 | 2028 Q1 | 2028 Q2 | 2028 Q3 | 2028 Q4 | Notes
Portal evidence share | KPI-06 | % | Higher | 0% | 10% | 30% | 45% | 55% | 57% | 60% | 61% | 62% | Quarterly path averages 35% in 2027 and 60% in 2028, matching the base business case.
Ops handling time per dispute | KPI-05 | minutes | Lower | 42 | 40 | 36 | 32 | 29 | 28 | 27 | 26 | 25 | Reaches the 25-minute target by end of 2028.
On-time response rate | KPI-03 | % | Higher | 78% | 82% | 86% | 89% | 91% | 92% | 93% | 94% | 95%
Missed-deadline loss rate | KPI-04 | % | Lower | 9% | 8.5% | 7% | 6% | 5% | 4.5% | 4% | 3.5% | 3%
Settlement contacts per 100 merchants | KPI-07 | count | Lower | 14 | 14 | 12.5 | 11 | 10 | 9.5 | 9 | 8.5 | 8 | Definition still Proposed in KPI catalog.
Dispute value recovery rate | KPI-01 | % | Higher | 38% | 38% | 39.5% | 41% | 42% | 43% | 44% | 44.5% | 45% | Pending CR-05 outcome definitions.
Quarterly actuals (enter each quarter)
Measure | KPI | Unit | Direction | Baseline | 2027 Q1 | 2027 Q2 | 2027 Q3 | 2027 Q4 | 2028 Q1 | 2028 Q2 | 2028 Q3 | 2028 Q4 | Notes
Portal evidence share | KPI-06 | % | Higher | 0%
Ops handling time per dispute | KPI-05 | minutes | Lower | 42
On-time response rate | KPI-03 | % | Higher | 78%
Missed-deadline loss rate | KPI-04 | % | Lower | 9%
Settlement contacts per 100 merchants | KPI-07 | count | Lower | 14
Dispute value recovery rate | KPI-01 | % | Higher | 38%
Status
Measure | KPI | Unit | Direction | Baseline | 2027 Q1 | 2027 Q2 | 2027 Q3 | 2027 Q4 | 2028 Q1 | 2028 Q2 | 2028 Q3 | 2028 Q4 | Notes
Portal evidence share | KPI-06 | % | Higher | 0% | – | – | – | – | – | – | – | –
Ops handling time per dispute | KPI-05 | minutes | Lower | 42 | – | – | – | – | – | – | – | –
On-time response rate | KPI-03 | % | Higher | 78% | – | – | – | – | – | – | – | –
Missed-deadline loss rate | KPI-04 | % | Lower | 9% | – | – | – | – | – | – | – | –
Settlement contacts per 100 merchants | KPI-07 | count | Lower | 14 | – | – | – | – | – | – | – | –
Dispute value recovery rate | KPI-01 | % | Higher | 38% | – | – | – | – | – | – | – | –
Annual benefits vs business case (base scenario, USD)
Year | Planned benefits |  | Actual benefits |  | Realization | Status
2027 (Y1) | 355542 |  |  |  | – | –
2028 (Y2) | 609500 |  |  |  | – | –
2029 (Y3) | 711083 |  |  |  | – | –
Planned benefits are copied from the Business_Case_GTM workbook (base scenario). Update them if the business case is refreshed at a review gate.

## Iteration Roadmap
Iteration Roadmap
Merchant Payment Operations & Dispute Hub · Simulation project · What the product does next, prioritized by value per unit of effort
Effort points: S=1, M=2, L=3, XL=5. Priority score = value ÷ effort points. Rank is unique.
ID | Initiative | Problem or opportunity | Source | Linked items | KPI impact | Horizon | Target quarter | Effort | Value (1-5) | Effort points | Priority score | Rank | Status | Owner | Decision gate | h_now | h_next | h_later
IR-01 | Pilot feedback fixes | Usability issues found by pilot merchants | Pilot feedback | CM-11, KPI-10 | KPI-10, KPI-18 | Now | 2027 Q1 | S | 4 | 1 | 4 | 1 | Planned | Product Owner | Pilot exit review | 1
IR-02 | Merchant satisfaction survey | No direct measure of merchant sentiment | KPI catalog gap | KPI-18 | KPI-18 | Now | 2027 Q1 | S | 3 | 1 | 3 | 3 | Planned | Product Owner | Monthly business review | 3
IR-03 | Evidence templates by reason code | Merchants unsure what evidence wins each dispute type | Pilot hypothesis; US-007 | US-007, KPI-01 | KPI-01, KPI-02 | Next | 2027 Q2 | M | 5 | 2 | 2.5 | 4 | Discovery | Product Owner | Wave 1 go / no-go |  | 4
IR-04 | Reason code admin screen | Rule updates still need engineering support | CR-02 Option C | CR-02, US-047 | Ops effort | Next | 2027 Q2 | M | 3 | 2 | 1.5 | 8 | Planned | Dispute Ops Lead | Quarterly roadmap review |  | 8
IR-05 | SMS deadline reminders | Urgent reminders missed when users are away from email | CR-09 | CR-09, US-027 | KPI-03, KPI-04 | Next | 2027 Q2 | M | 3 | 2 | 1.5 | 9 | Idea | Product Owner | CR-09 decision |  | 9
IR-06 | Fraud case management in the hub | Analysts switch systems to see and act on fraud cases | CR-01 Phase 2 commitment | CR-01, US-045, D-07 | KPI-05 | Next | 2027 Q3 | XL | 4 | 5 | 0.8 | 11 | Discovery | Fraud Operations Lead | Phase 2 funding decision |  | 11
IR-07 | Spanish language portal | Spanish-speaking merchants rely on a PDF guide | CR-04 deferral | CR-04, US-046 | KPI-06 | Next | 2027 Q3 | L | 3 | 3 | 1 | 10 | Planned | Merchant Relationship Lead | Phase 2 funding decision |  | 10
IR-08 | Recurring billing and travel evidence guidance | Wave 2 segments have complex evidence needs | Segment prioritization | Rollout Plan Wave 2 | KPI-01, KPI-06 | Next | 2027 Q2 | S | 4 | 1 | 4 | 2 | Planned | Merchant Relationship Lead | Wave 2 go / no-go |  | 2
IR-09 | Auto-accept rules for low-value disputes | Merchants spend time on disputes not worth contesting | Ops insight | KPI-05 | KPI-05 | Later | 2027 Q4 | M | 4 | 2 | 2 | 6 | Idea | Product Owner | Post-implementation review |  |  | 6
IR-10 | Marketplace sub-merchant model | Marketplaces can't manage disputes for sub-merchants | Segment prioritization | Segments: Marketplaces | KPI-06 | Later | 2028 Q1 | XL | 4 | 5 | 0.8 | 12 | Idea | Product Owner | 2028 planning |  |  | 12
IR-11 | Evidence quality checks before submission | Weak evidence leads to avoidable losses | KPI-02 analysis | KPI-02 | KPI-01, KPI-02 | Later | 2028 Q2 | L | 5 | 3 | 1.67 | 7 | Idea | Product Owner | 2028 planning |  |  | 7
IR-12 | Retire email dispute intake | Parallel email channel keeps ops cost high | Business case | Rollout Plan Phase 4, KPI-06 | KPI-05, KPI-06 | Next | 2027 Q4 | M | 5 | 2 | 2.5 | 5 | Planned | Dispute Ops Lead | General availability go / no-go |  | 5

## BAU Transition
BAU Transition
Merchant Payment Operations & Dispute Hub · Simulation project · Moving ownership from the delivery team to business-as-usual teams
Update Status as each handover is accepted by the receiving team.
ID | Area | Handover item | From | To | Due date | Status | Acceptance criteria
BT-01 | Support | Runbooks for top 10 incident scenarios | Delivery squads | Run team | 2027-01-15 | Not Started | Run team walks through each runbook and signs off (EX-09)
BT-02 | Support | On-call rota and incident manager role | Tech Lead | Run Team Lead | 2027-01-22 | Not Started | Run team covers two consecutive weeks of on-call without delivery squad escalation
BT-03 | Support | Monitoring dashboards and alert ownership | Tech Lead | Run Team Lead | 2027-01-22 | Not Started | Alert routing updated; false positive rate under 10% (EX-08)
BT-04 | Product | Product backlog and roadmap ownership | Delivery partner Product Owner | Client product owner | 2027-03-12 | Not Started | Client product owner runs two refinement sessions and one sprint review
BT-05 | Product | Decision, RAID and change log archive | Project Manager | Client PMO | 2027-01-29 | Not Started | Open items transferred with owners; closed items archived
BT-06 | Data | KPI dashboards and data definitions | Product Owner | Finance Lead and Dispute Ops Lead | 2027-02-26 | Not Started | Owners publish one monthly business review pack without delivery team help
BT-07 | Data | Analytics tracking plan maintenance | Product Owner | Data Governance Lead | 2027-02-26 | Not Started | Tracking plan change process documented and approved
BT-08 | Technology | Access, credentials and environment ownership | Tech Lead | Client technology team | 2027-01-22 | Not Started | Delivery partner access reviewed and removed or re-approved
BT-09 | Technology | Vendor contacts, contracts and support SLAs | Project Manager | Vendor Manager | 2027-01-29 | Not Started | Processor and storage vendor escalation contacts confirmed
BT-10 | Knowledge | Knowledge transfer sessions (architecture, integrations, data) | Delivery squads | Client engineering and run team | 2027-02-12 | Not Started | Attendance recorded; recordings and Q&A log stored
BT-11 | Operations | Dispute ops procedures updated for portal-first process | Dispute Ops Lead | Dispute ops team | 2027-01-08 | In Progress | Procedures published; team trained
BT-12 | Commercial | Warranty period and defect support terms | Engagement Lead | Business Sponsor | 2027-01-22 | Not Started | Warranty scope, duration and exit agreed in writing
Email dispute intake retirement
Wave |  | Date | Action |  |  | Criteria to proceed | Owner
Wave 1 |  | 2027-03-15 | Auto-reply on dispute mailbox points Wave 1 merchants to the portal |  |  | Wave 1 onboarding started | Dispute Ops Lead
Wave 1 |  | 2027-05-28 | Stop accepting emailed evidence from onboarded Wave 1 merchants (assisted exceptions only) |  |  | Portal share at least 35% in Wave 1 merchants; no open Sev 1 or Sev 2 | Dispute Ops Lead
Wave 2 |  | 2027-09-24 | Stop accepting emailed evidence from Wave 2 merchants |  |  | Wave 2 exit gates met | Dispute Ops Lead
General availability |  | 2027-12-17 | Retire email intake for all portal-enabled merchants; keep assisted channel for accessibility and exceptions |  |  | GA exit gates met; ops capacity plan agreed (LR-17) | Business Sponsor

## Reviews & Lessons
Reviews & Lessons Learned
Merchant Payment Operations & Dispute Hub · Simulation project · Decision reviews after launch and lessons carried forward
Review calendar
ID | Review | Date | Purpose | Inputs | Decision or output | Chair | Status | Days from reporting date | h
RV-01 | Go-live go / no-go | 2026-12-04 | Confirm launch readiness | Launch readiness checklist, UAT exit, security sign-off | Go-live decision | Steering Committee | Scheduled | 85 | 2026-12-04
RV-02 | Hypercare exit review | 2027-01-22 | Confirm stability and handover to run team | Hypercare exit criteria, BAU transition status | Hypercare exit decision | Tech Lead | Scheduled | 134 | 2027-01-22
RV-03 | Pilot exit review | 2027-03-11 | Decide whether to proceed to Wave 1 | Pilot results report, KPI exit gates | Wave 1 go / no-go | Steering Committee | Scheduled | 182 | 2027-03-11
RV-04 | Post-implementation review | 2027-04-15 | Assess delivery, early benefits and lessons learned | Lessons log, benefits tracker Q1, incident summary | Improvement actions; business case refresh | Business Sponsor | Scheduled | 217 | 2027-04-15
RV-05 | Quarterly benefits review (Q1) | 2027-04-22 | Compare Q1 benefits with plan | Benefits tracker | Benefits status; corrective actions | Steering Committee | Scheduled | 224 | 2027-04-22
RV-06 | Wave 2 go / no-go | 2027-06-03 | Decide whether to proceed to Wave 2 | Wave 1 exit gates, benefits tracker | Wave 2 decision | Steering Committee | Scheduled | 266 | 2027-06-03
RV-07 | Quarterly benefits review (Q2) | 2027-07-22 | Compare Q2 benefits with plan | Benefits tracker | Benefits status; corrective actions | Steering Committee | Scheduled | 315 | 2027-07-22
RV-08 | General availability go / no-go | 2027-09-30 | Decide whether to launch to all merchants | Wave 2 exit gates, ops capacity plan | GA decision | Steering Committee | Scheduled | 385 | 2027-09-30
RV-09 | Quarterly benefits review (Q3) | 2027-10-21 | Compare Q3 benefits with plan | Benefits tracker | Benefits status; corrective actions | Steering Committee | Scheduled | 406 | 2027-10-21
RV-10 | Annual benefits review (Year 1) | 2028-01-27 | Year 1 benefits vs business case; Phase 2 priorities | Benefits tracker, roadmap, KPI results | Year 2 targets; Phase 2 scope | Business Sponsor | Scheduled | 504 | 2028-01-27
Lessons learned log
ID | Phase | What happened |  | Impact | Lesson | Action for next phase |  | Owner
LL-01 | Build | Processor sandbox returned inconsistent status values |  | Webhook story blocked; status mapping defect in SIT | Validate vendor sandboxes against documented values during discovery | Add contract tests for processor status values; include in vendor onboarding checklist |  | Tech Lead | I-01, DEF-03
LL-02 | Build | Finance and ops defined dispute win rate differently |  | Reporting stories stalled; decision escalated | Agree KPI definitions with owners before building reports | Hold a KPI definition workshop at the start of each new metric-heavy epic |  | Product Owner | I-05, CR-05
LL-03 | Build | Penetration test slot booked too late |  | UAT start at risk; CR-06 raised | Book security testing slots at mobilization, not mid-build | Add security testing dates to the mobilization checklist |  | Project Manager | D-03, CR-06
LL-04 | Build | Design sign-off waited two weeks for stakeholder review |  | Sprint 5 refinement blocked | Time-box design reviews and name one approver | Design authority approves within 5 business days or escalates |  | Product Owner | I-03
LL-05 | Build | Analytics tracking plan reached data governance late |  | Pilot adoption metrics blocked | Involve data governance when the tracking plan is first drafted | Add data governance to Definition of Ready for analytics stories |  | Product Owner | I-06
LL-06 | Build | Approved change swapped into sprint using a similar-sized story |  | No release impact; clear audit trail | Swapping stories keeps scope stable when a small change is urgent | Keep swap-and-note practice; record the swapped story in Notes |  | Product Owner | CR-07, US-017
Formulas:
h = IF(AND([Date]<>"",N([Days from reporting date])>=0,[Status]<>"Complete"),[Date]+ROW()/100000,"")